## Worksheet
Task ID | Task Name | Owner | Due Date | Status | Priority | Estimated Effort (hrs) | Budget Allocation ($) | Actual Cost ($) | Progress (%)
WF-001 | Requirement Gathering & Analysis | Sarah Chen | 2024-03-15 | In Progress | High | 40 | 12,000.00 | 8,500.00 | 72%
WF-002 | Process Flow Design | David Kim | 2024-04-10 | Not Started | Medium | 30 | 9,500.00 | 0 | 0%
WF-003 | System Integration Planning | Lisa Park | 2024-05-05 | On Hold | High | 60 | 18,000.00 | 12,300.00 | 45%
WF-004 | User Acceptance Testing | James Reed | 2024-06-15 | Planned | Medium | 25 | 7,500.00 | 0 | 0%
WF-005 | Post-Implementation Review | Anna Torres | 2024-07-30 | Not Started | Low | 15 | 3,000.00 | 0 | 0%