## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Estimated Hours | Progress (%)
T-001 | Requirement Gathering Meeting | Alex Turner | 2023-10-05 | High | In Progress | 4 | 65%
T-002 | UI/UX Design Finalization | Samira Chen | 2023-10-15 | High | Not Started | 8 | 0%
T-003 | Backend API Development | Jordan Lee | 2023-10-25 | Critical | In Progress | 16 | 40%
T-004 | Performance Testing | Morgan Wright | 2023-11-05 | Medium | Not Started | 6 | 0%
T-005 | User Training Documentation | Taylor Reed | 2023-10-30 | Low | Pending Review | 4 | 30%