## Worksheet
Task ID | Task Name | Owner | Due Date | Priority | Status | Progress (%) | Notes
T-001 | Market Research Phase | Alex Morgan | 2024-03-15 | High | In Progress | 65% | Initial competitor analysis complete. Need to finalize customer survey.
T-002 | Product Roadmap Planning | Jamie Lee | 2024-03-28 | Medium | Not Started | 0% | Draft outline in progress. Waiting for feedback from design team.
T-003 | UI/UX Design Review | Sam Patel | 2024-04-10 | High | Completed | 100% | Final design approved by stakeholders. Ready for dev handoff.
T-004 | Development Sprint Kickoff | Taylor Reed | 2024-04-15 | High | Not Started | 0% | Team to finalize tech stack and assign sprint goals.
T-005 | Performance Testing | Jordan Kim | 2024-05-05 | Medium | Planned | 0% | Scheduled after beta release. Will assess load capacity.