## Worksheet
Task ID | Task Name | Owner | Due Date | Status | Priority | Estimated Time (hrs) | Dependencies | Progress (%)
T-001 | Project Kickoff Meeting | Jane Doe | 2024-04-01 | Completed | Medium | 2.5 | - | 100%
T-002 | Requirements Gathering | John Smith | 2024-04-15 | In Progress | High | 8 | T-001 | 65%
T-003 | UI/UX Design Phase | Alex Chen | 2024-05-10 | Planned | Medium | 12 | T-002 | 0%
T-004 | Development Sprint 1 | Team A | 2024-06-05 | Not Started | High | 30 | T-003 | 0%
T-005 | Testing & QA | Sarah Lee | 2024-07-15 | Planned | Medium | 18 | T-004 | 0%