## Worksheet
Date | Task Name | Workflow Stage | Start Time | End Time | Duration (min) | Status | Assigned To | Priority Level | Notes
2024-04-01 | Client Onboarding | Initial Contact | 09:00 | 10:30 | 90 | Completed | Sarah Johnson | High | Submitted required documents and set up portal access.
2024-04-02 | Requirements Gathering | Analysis Phase | 14:00 | 16:15 | 135 | In Progress | David Chen | High | Client provided detailed use cases and feedback.
2024-04-03 | Process Design | Design Phase | 10:15 | 13:45 | 210 | Completed | Lisa Park | Medium | Finalized workflow diagram with approval from client.
2024-04-04 | Team Alignment Meeting | Review & Sync | 15:30 | 16:30 | 60 | Completed | Team Lead | Low | Discussed milestones and next steps.
2024-04-05 | Training Session Setup | Implementation Prep | 09:30 | 11:15 | 105 | Pending | Mark Taylor | Medium | Waiting for client schedule confirmation.