## Worksheet
Task | Assigned To | Start Date | End Date | Duration (hrs) | Status | Priority | Progress (%)
Requirement Gathering | John Doe | 2024-04-01 | 2024-04-10 | 40 | In Progress | High | 65%
UI/UX Design | Sarah Lee | 2024-04-11 | 2024-04-25 | 35 | Planned | Medium | 30%
Development Phase | Mike Chen | 2024-04-26 | 2024-05-15 | 80 | Not Started | High | 0%
Testing & QA | Lisa Wong | 2024-05-16 | 2024-05-31 | 45 | Planned | Medium | 0%
Deployment & Review | Team Lead | 2024-06-01 | 2024-06-05 | 15 | Not Started | Low | 0%