## Worksheet
Task | Owner | Due Date | Priority | Status | Estimated Time (min) | Dependencies | Action Required
Conduct workflow audit of current processes | Alex Morgan | 2024-04-15 | High | In Progress | 120 | None | Review findings and present to leadership
Identify bottlenecks in approval workflows | Jordan Lee | <2024-04-20 | Medium | Pending | 90 | Audit complete | Submit analysis report by end of week
Redesign form submission process | Samira Patel | 2024-05-05 | High | Not Started | 180 | Bottleneck report approved | Finalize user flow and prototype
Implement automated notifications in workflow system | David Chen | 2024-05-10 | Medium | Planning | 150 | Form redesign complete | Set up test environment and schedule rollout
Conduct end-user training session on new workflow tools | Lena Rodriguez | 2024-05-15 | Low | Scheduled | 60 | Notification system live in test | Send pre-training email and collect feedback