## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%)
Conduct workflow audit of current processes | Jane Doe | 2024-04-15 | In Progress | High | 60%
Identify bottlenecks and inefficiencies | John Smith | 2024-04-20 | Not Started | High | 0%
Redesign key workflow steps | Lisa Chen | 2024-05-05 | Planned | Medium | 10%
Implement automation tools | Mike Johnson | 2024-05-15 | Not Started | High | 0%
Train team on new workflow procedures | Sarah Lee | 2024-06-01 | Not Started | Medium | 0%