## Worksheet
Task ID | Task Description | Owner | Due Date | Priority Level | Status | Estimated Effort (hrs) | Dependencies | Notes | Assigned Team
WFO-001 | Conduct workflow audit of current approval processes | Alex Morgan | 2024-03-15 | High | In Progress | 8 | None | Review all current approvals and document bottlenecks. | Process Analysis Team
WFO-002 | Redesign approval workflow for HR onboarding | Jordan Lee | <2024-04-10 | High | Not Started | 12 | WFO-001 completion | Include new digital form integration and manager sign-off. | HR & Operations Team
WFO-003 | Implement automated notifications in workflow system | Samira Patel | 2024-04-25 | Medium | Planned | 6 | WFO-002 approval design ready | Integrate with existing email and internal messaging. | IT & Automation Team
WFO-004 | Train department heads on new workflow tools | Ryan Kim | 2024-05-15 | Medium | Not Started | 4 | WFO-003 completed | Sessions to be scheduled with feedback collection. | Training & Compliance Team
WFO-005 | Monitor KPIs post-implementation for 30 days | Taylor Reed | 2024-06-15 | Low | Not Started | 3 | WFO-002 & WFO-003 completed | Report on cycle time reduction and error rate. | Analytics & Operations Team