## Worksheet
Task | Owner | Due Date | Status | Priority (1-5) | Budget Allocation ($) | Progress (%)
Conduct Process Mapping of Current Workflow | Jane Smith | 2024-04-15 | In Progress | 4 | 2,500 | 65%
Identify Bottlenecks in Approval Process | Michael Lee | <2024-04-20 | Pending | 5 | 3,000 | 0%
Implement Automated Notifications | Sarah Chen | 2024-05-05 | Not Started | 3 | 1,800 | 0%
Review KPIs Post-Optimization | David Ross | 2024-05-20 | Not Started | 2 | 1,500 | 0%
Train Team on New Workflow Procedures | Lisa Wong | 2024-06-01 | Planned | 4 | 2,200 | 15%