## Worksheet
Task | Owner | Due Date | Priority | Status | Notes
Conduct workflow audit of current processes | Jane Doe | 2024-04-10 | High | In Progress | Review all departmental workflows for bottlenecks and redundancies.
Design new approval workflow for procurement | Michael Chen | 2024-04-18 | High | Planned | Include dual approval for over $5,000 requests.
Implement automated notifications in workflow system | Sarah Kim | 2024-05-03 | Medium | Pending | Configure system to send reminders 24 hours before deadlines.
Train department heads on new workflow tools | David Wong | 2024-04-25 | Medium | Completed | Session held on April 20 with attendance of all department leads.
Monitor KPIs post-implementation | Linda Patel | Ongoing | Low | Active | Weekly reporting to be shared with executive team.