## Worksheet
Task | Owner | Due Date | Priority | Status | Notes
Review current workflow process | Team Lead | 2023-10-05 | High | Pending | Analyse bottlenecks and inefficiencies in existing steps.
Identify key performance indicators (KPIs) | Operations Analyst | 2023-10-12 | Middle | In Progress | Define measurable goals for workflow efficiency.
Design optimized workflow diagram | Design Team | 2023-10-19 | High | Not Started | Create visual flow with decision points and handoffs.
Conduct team workshop for feedback | Team Lead | 2023-10-26 | Middle | Planned | Gather input from all departments on proposed changes.
Implement new workflow in pilot phase | Operations Manager | 2023-11-05 | High | Not Started | Test with one department before full rollout.
Evaluate results and adjust process | Quality Assurance | 2023-11-15 | High | Pending | Analyze data to determine effectiveness and refine.