## Worksheet
Task | Owner | Due Date | Status | Priority | Progress % | Notes
Review current workflow process | Alex Chen | 2024-04-10 | In Progress | High | 65% | Identify bottlenecks in approval stages.
Map all key touchpoints | Jordan Lee | <2024-04-15 | Pending | Medium | 0% | Prepare visual flowchart for stakeholders.
Propose workflow redesign | Samira Patel | 2024-04-25 | Not Started | High | 0% | Draft new process with automation suggestions.
Conduct stakeholder feedback session | Michael Torres | 2024-05-03 | In Progress | Medium | 40% | Schedule meeting with department leads.
Finalize and implement new workflow | Team Lead | 2024-05-15 | Not Started | High | 0% | Roll out changes after approval and testing.