## Worksheet
Week | Project Phase | Task Description | Allocated Budget (USD) | Actual Spend (USD) | Variance (USD) | Status | Owner | Timeline
Week 1 | Feasibility Study | Market analysis and stakeholder interviews | 15,000 | 14,200 | 800 | On Track | Sara Lin | Mon - Wed, 9:00 AM - 4:00 PM
Week 2 | Design Development | UI/UX wireframes and prototype creation | 25,000 | 24,800 | 200 | On Track | Mike Chen | Tue - Fri, 10:00 AM - 6:00 PM
Week 3 | Development Sprint | Frontend and backend coding implementation | 50,000 | 49,500 | 500 | On Track | Lena Park | Mon - Fri, 9:00 AM - 5:00 PM
Week 4 | Testing & QA | Bug identification and user acceptance testing | 20,000 | 19,750 | 250 | On Track | James Reed | Wed - Sat, 8:00 AM - 4:00 PM
Week 5 | Deployment & Review | Production deployment and final stakeholder review | 10,000 | 10,200 | -200 | At Risk | Amira Khan | Fri - Sun, 9:00 AM - 1:00 PM