## Worksheet
Date | Task | Responsible | Time Allocation (hrs) | Budget (USD) | Status | Notes
Mon, Apr 8 | Review workflow process maps | Jane Smith | 2.5 | 200 | Pending | Align with engineering team for feedback.
Tue, Apr 9 | Optimize approval workflows | Mark Johnson | <3.0300.00 | In Progress | Testing new routing logic.
Wed, Apr 10 | Implement daily reporting dashboard | Lisa Chen | 4 | 450 | Planned | To be integrated with CRM system.
Thu, Apr 11 | Conduct cross-departmental review | Team Lead | 3.5 | 350 | Pending | Schedule stakeholder meeting.
Fri, Apr 12 | Update weekly budget forecast | Finance Officer | 1.5 | 150 | Completed | Draft submitted to management.