## Worksheet
Week | Activity | Responsible Party | Budget (USD) | Status | Notes
1 | Initial Workflow Assessment | Operations Manager | 2,500 | Completed | Review of current processes and inefficiencies identified.
2 | Process Mapping & Documentation | Process Analyst | 3,200 | In Progress | Mapping completed for 8 key workflows.
3 | Automation Pilot Implementation | IT & Dev Team | 4,000 | Scheduled | Pilot to run in finance department.
4 | Stakeholder Training Sessions | HR & Training Unit | 1,800 | Completed | All departments trained on new tools.
5 | Performance Monitoring & Review | Operations Manager | 2,000 | In Progress | Data collected from pilot phase.
Total Budget |  |  |  |  | $13,500