## Worksheet
Week | Project Name | Task Description | Assigned Team | Start Date | End Date | Estimated Hours | Budget Allocation ($) | Status | Progress (%)
Week 1 | Customer Onboarding Flow | Design and implement initial onboarding workflow | Product Team | 04/01/2024 | 04/07/2024 | 8 | 800 | In Progress | 45%
Week 2 | Workflow Automation Review | Evaluate current automation processes and identify bottlenecks | Operations & Analytics Team | 04/08/2024 | 04/14/2024 | 6 | 600 | Not Started | 0%
Week 3 | Performance Metrics Dashboard | Develop KPI dashboard for workflow monitoring | Data Science Team | 04/15/2024 | 04/21/2024 | 10 | 1,000 | Planned | 0%
Week 4 | Team Training Session | Conduct training on new workflow tools and systems | HR & Learning Team | 04/22/2024 | 04/28/2024 | 5 | 500 | Pending Approval | 0%
Week 5 | Process Optimization Review | Conduct cross-functional review of optimized workflows | All Teams (Joint) | 04/29/2024 | 05/05/2024 | 15 | 1,500 | Not Started | 0%