## Worksheet
Week | Activity | Responsible Party | Start Date | End Date | Estimated Hours | Budget Allocation ($) | Status
Week 1 | Workflow Audit & Gap Analysis | Operations Manager | 2024-04-01 | 2024-04-07 | 8 | 800 | Planned
Week 2 | Process Mapping for Key Workflows | Process Engineer | 2024-04-08 | 2024-04-14 | 10 | 1,000 | In Progress
Week 3 | Automation Tool Implementation | <IT Team & Workflow Lead | 2024-04-15 | 2024-04-21 | 15 | 1,500 | Pending Approval
Week 4 | Performance Metrics Setup & KPIs Definition | Finance & Operations Team | 2024-04-22 | 2024-04-28 | 6 | 600 | Scheduled
Week 5 | Stakeholder Review & Feedback Loop | Project Steering Committee | 2024-04-29 | 2024-05-05 | 4 | 400 | Pending Meeting
Total Budget: |  |  | $4,300