## Worksheet
Week | Date Range | Objective | Tasks | Responsible Person | Due Date | Status | Notes / Actions
1 | Mon, Apr 8 - Sun, Apr 14 | Optimize approval workflow in HR onboarding process | Streamline form submissions Reduce redundant checks Set up automated reminders | Sarah Kim | Apr 14 | In Progress | Review feedback from pilot group
2 | Mon, Apr 15 - Sun, Apr 21 | Automate routine reporting to stakeholders | Set up weekly reports Integrate with BI tool Create templates | David Lee | <Apr 21 | Planned | Sync with Finance team for data access
3 | Mon, Apr 22 - Sun, Apr 28 | Reduce response time in support tickets by 30% | Implement priority tagging Create SLA tracking Train team on escalation paths | Lisa Wong | Apr 28 | Not Started | Need access to ticketing logs
4 | Mon, Apr 29 - Sun, May 5 | Refine communication flow between departments | Map current workflows Create a shared playbook Conduct cross-team review meeting | James Reed | May 5 | Not Started | Schedule team workshop on May 2
5 | Mon, May 6 - Sun, May 12 | Implement feedback loop for process improvements | Launch post-implementation survey Analyze results Identify top changes | Elena Torres | May 12 | Planned | Share survey link with all teams by May 3