## Worksheet
Week | Date Range | Workflow Step | Owner | Due Date | Status | Notes
Week 1 | Mon, Apr 8 – Sun, Apr 14 | Task Initiation & Review | John Smith | Apr 8, 2024 | Completed | Initial workflow documentation approved.
Week 1 | Mon, Apr 8 – Sun, Apr 14 | Resource Allocation | Sarah Lee | Apr 10, 2024 | In Progress | Team assignments confirmed. Pending budget approval.
Week 2 | Mon, Apr 15 – Sun, Apr 21 | Process Validation | David Chen | Apr 18, 2024 | Planned | Testing phase scheduled with QA team.
Week 2 | Mon, Apr 15 – Sun, Apr 21 | Performance Metrics Setup | Linda Park | Apr 20, 2024 | Pending | Waiting for data sources to be integrated.
Week 3 | Mon, Apr 22 – Sun, Apr 28 | Feedback Collection & Review | Mike Torres | Apr 25, 2024 | Completed | All stakeholder feedback collected and analyzed.
Week 3 | Mon, Apr 22 – Sun, Apr 28 | Workflow Adjustment Plan | John Smith | Apr 27, 2024 | In Progress | Proposed changes under review by leadership.