## Worksheet
Week | Task | Owner | Due Date | Status | Priority
Q1 Week 1 | Review Q1 goals and objectives | Project Lead | 2024-03-05 | In Progress | High
Q1 Week 2 | Finalize workflow process map | Process Analyst | 2024-03-12 | Not Started | High
Q1 Week 3 | Conduct team workshop on optimization | Team Manager | 2024-03-19 | Planned | Medium
Q1 Week 4 | Implement pilot phase of optimized workflow | Operations Lead | 2024-03-26 | Not Started | High
Q2 Week 1 | Analyze pilot results and feedback | QA Officer | 2024-04-02 | Not Started | Medium
Q2 Week 2 | Adjust workflow based on feedback | Project Lead | 2024-04-09 | Planned | High
Q2 Week 3 | Train team on revised workflow | HR & Training Lead | 2024-04-16 | Not Started | Medium
Q2 Week 4 | Conduct full-scale rollout and monitoring | Operations Director | 2024-04-23 | Planned | High