Purchase Order - Architect Services - Algeria Algiers
PURCHASE ORDER
Atelier Bâtiment & Ingénierie SARL
12, Rue Didouche Mourad, Hydra, 16000 Algiers, Algeria
RC: 16/00-1234567B23 | NIF: 000123456789012 | NIS: 000123456789012
Tel: +213 (0)23 45 67 89 | Email: procurement@atelier-batiment.dz
Purchase Order No.: PO-2025-ALG-00472
Date of Issue: 15 June 2025
Valid Until: 15 July 2025
Project Reference: PRJ-ALG-2025-089
Location: Algeria Algiers, Hydra District
Priority: High
1. Vendor / Service Provider Information
	Field
	Details

	Company Name
	Cabinet d'Architecture Benali & Associés

	Architect of Record
	Mr. Karim Benali, Diplômé d'État en Architecture (DEA), Ordre des Architectes d'Algérie, Member No. 16-0045

	Address
	45, Boulevard Zighout Youcef, 16000 Algiers, Algeria

	Contact
	Tel: +213 (0)23 55 44 33 | Email: k.benali@archi-benali.dz

	Professional License
	Architect License No. ALG-ARC-2019-0087, issued by the Ministry of Housing and Urban Planning, Algeria

	Bank Details
	BNA Algiers – Hydra Branch | RIB: 007 00012 3456789012 34 | IBAN: DZ76 0070 0012 3456 7890 1234


2. Description of Services – Architect Engagement
This Purchase Order is issued by Atelier Bâtiment & Ingénierie SARL (hereinafter referred to as the "Client") to formally engage the services of Cabinet d'Architecture Benali & Associés (hereinafter referred to as the "Architect") for the design, planning, and architectural supervision of a mixed-use commercial and residential building located in the Hydra district of Algeria Algiers. The Architect shall be responsible for all phases of architectural design in full compliance with the Algerian Urban Planning Code (Code de l'Urbanisme et de la Construction), the local zoning regulations of the Wilaya of Algiers, and all applicable national building standards.
The scope of work for the Architect encompasses, but is not limited to: preliminary site analysis and feasibility studies; conceptual design development; production of full architectural drawings (floor plans, elevations, sections, and details); structural coordination; interior design specifications; landscape architecture integration; preparation of all documentation required for the building permit (permis de construire) from the Direction de l'Urbanisme et de la Construction de la Wilaya d'Algiers; and on-site architectural supervision during the construction phase.
3. Schedule of Deliverables and Fees
	Item No.
	Description of Architect Service
	Phase
	Unit
	Quantity
	Unit Price (DZD)
	Total (DZD)

	01
	Site survey, topographic analysis, and feasibility report for the Algeria Algiers plot
	Phase 1
	Lump Sum
	1
	450,000
	450,000

	02
	Conceptual design package (3 options) with 3D renderings
	Phase 2
	Lump Sum
	1
	1,200,000
	1,200,000

	03
	Detailed architectural drawings, specifications, and BOQ preparation
	Phase 3
	Lump Sum
	1
	2,800,000
	2,800,000

	04
	Building permit application preparation and submission to Algiers municipal authorities
	Phase 3
	Lump Sum
	1
	350,000
	350,000

	05
	On-site architectural supervision (18 months, 3 visits per month)
	Phase 4
	Month
	18
	180,000
	3,240,000

	06
	As-built documentation and final handover report
	Phase 5
	Lump Sum
	1
	500,000
	500,000

	SUBTOTAL (DZD)
	8,540,000

	VAT (19%) – Algeria
	1,622,600

	GRAND TOTAL (DZD)
	10,162,600


4. Payment Terms
Payment for the Architect's services under this Purchase Order shall be made in Algerian Dinars (DZD) via bank transfer to the account specified in Section 1. The payment schedule is as follows: 20% advance payment upon signature of this Purchase Order; 30% upon approval of the conceptual design; 30% upon submission of detailed drawings and receipt of the building permit; and 20% upon completion of the on-site supervision phase and delivery of as-built documentation. Invoices must be submitted in triplicate and must reference this Purchase Order number (PO-2025-ALG-00472). Payment shall be processed within thirty (30) calendar days of receipt of a valid invoice. Late payments shall accrue interest at the rate of 1.5% per month in accordance with Algerian commercial law.
5. Terms and Conditions
5.1 This Purchase Order is governed by the laws of the People's Democratic Republic of Algeria, including the Algerian Civil Code, the Commercial Code, and the specific regulations governing the architectural profession as set forth by the Ordre des Architectes d'Algérie.
5.2 The Architect warrants that all deliverables shall be original, free from intellectual property infringement, and compliant with the Algerian building code (Réglementation de construction parasismique – RPA 2021) and the thermal regulations applicable in the Algeria Algiers climate zone.
5.3 The Architect shall maintain professional liability insurance with a minimum coverage of 50,000,000 DZD throughout the duration of the engagement. A certificate of insurance shall be provided prior to the commencement of Phase 2.
5.4 Any modifications to the scope of work must be agreed upon in writing through a formal amendment to this Purchase Order. The Client reserves the right to request up to three (3) design revisions per phase at no additional cost; further revisions shall be billed at the Architect's standard hourly rate of 8,000 DZD per hour.
5.5 The Architect shall comply with all data protection and confidentiality obligations. All project documents, site plans, and proprietary information related to this project in Algeria Algiers shall be treated as confidential and shall not be disclosed to third parties without prior written consent from the Client.
5.6 In the event of a dispute arising from this Purchase Order, the parties shall first attempt resolution through amicable negotiation. Failing resolution within thirty (30) days, the matter shall be submitted to the competent commercial court of Algiers, Algeria.
6. Project Timeline
	Milestone
	Target Date
	Deliverable

	Phase 1 – Site Analysis
	30 June 2025
	Feasibility Report

	Phase 2 – Conceptual Design
	31 August 2025
	Design Package + 3D Models

	Phase 3 – Detailed Design & Permit
	30 November 2025
	Full Drawings + Permis de Construire

	Phase 4 – Construction Supervision
	31 May 2027
	Monthly Supervision Reports

	Phase 5 – Handover
	30 June 2027
	As-Built Documentation


Important Notes: This Purchase Order is valid for acceptance within thirty (30) days of the issue date. The Architect must confirm acceptance in writing by returning a signed copy of this document. All communications regarding this Purchase Order shall be directed to the procurement department of Atelier Bâtiment & Ingénierie SARL, Algiers, Algeria. This document constitutes a binding contractual agreement upon countersignature by both parties. The Architect acknowledges that all work shall be performed in accordance with the professional ethics and standards established by the Ordre des Architectes d'Algérie and the relevant decrees of the Ministry of Housing, Urban Planning, and the City (Ministère de l'Habitat, de l'Urbanisme et de la Ville).
For and on behalf of the Client:
Atelier Bâtiment & Ingénierie SARL
Name: ___________________________
Title: Director of Procurement
Signature & Company Seal:
Date: ___________________________
For and on behalf of the Architect:
Cabinet d'Architecture Benali & Associés
Name: Karim Benali, Architect
Title: Principal Architect
Signature & Professional Seal:
Date: ___________________________
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