Purchase Order - Architect Services - India Bangalore
PURCHASE ORDER
Professional Architect Services – Residential & Commercial Design Project
Issued in India Bangalore, Karnataka, India
PO No: BLR-ARC-2025-00472
1. Purchase Order Details
	Field
	Details

	Purchase Order Number
	BLR-ARC-2025-00472

	Date of Issue
	14 June 2025

	Place of Issue
	India Bangalore, Karnataka 560001

	Valid Until
	14 July 2025

	Project Reference
	BLR-RES-2025-Phase-2


2. Purchasing Party (Buyer)
	Field
	Details

	Company Name
	Deccan Urban Development Pvt. Ltd.

	Registered Address
	4th Floor, Prestige Tech Park, Outer Ring Road, India Bangalore, Karnataka 560103

	GSTIN
	29AAXCD4821F1Z5

	Contact Person
	Mr. Rajesh Kumar, Director – Projects

	Email / Phone
	projects@deccanurban.in / +91-80-4112-7788


3. Supplier / Service Provider (Architect)
	Field
	Details

	Firm Name
	Studio Meridian Architects & Planners

	Lead Architect
	Ms. Ananya Deshpande, Principal Architect (COA Reg. No: KA/ARC/2011/03487)

	Office Address
	212, 1st Floor, Indiranagar 100 Ft Road, India Bangalore, Karnataka 560038

	GSTIN
	29ABFSD6743K1Z8

	Contact Person
	Ms. Ananya Deshpande, Principal Architect

	Email / Phone
	ananya@studiomeridian.in / +91-80-2521-4455


4. Scope of Architect Services
This Purchase Order is issued by Deccan Urban Development Pvt. Ltd. to engage the services of Studio Meridian Architects & Planners, a registered Architect firm operating in India Bangalore, for the complete architectural design, planning, and documentation of a mixed-use residential and commercial development project located in Whitefield, India Bangalore. The Architect shall be responsible for all phases of design delivery as enumerated below.
	Sr. No.
	Service / Deliverable
	Quantity / Area
	Rate (INR)
	Amount (INR)

	1
	Concept Design & Feasibility Study – Architectural massing, site analysis, and zoning compliance for the project plot in India Bangalore
	1 Project (42,000 sq.ft. GFA)
	1,85,000
	1,85,000

	2
	Schematic Design Development – Floor plans, elevations, sections, and 3D visualisations prepared by the Architect
	1 Project
	4,20,000
	4,20,000

	3
	Detailed Design & Working Drawings – Complete set of architectural drawings, specifications, and BOQ for statutory approvals in India Bangalore
	1 Project
	6,75,000
	6,75,000

	4
	Statutory Approvals & Liaison – Filing and follow-up with BBMP, BDA, and Karnataka State Building Code authorities in India Bangalore
	1 Project
	2,50,000
	2,50,000

	5
	Construction Supervision & Site Visits – Architect to conduct bi-weekly site inspections and issue RFIs during construction phase
	24 Visits (18 months)
	35,000
	8,40,000

	6
	Interior Design Coordination – Architect to coordinate with interior consultants for common areas and amenity spaces
	1 Project
	1,90,000
	1,90,000

	7
	As-Built Documentation & Handover – Final architectural as-built drawings and O&M manuals
	1 Project
	1,20,000
	1,20,000

	Subtotal (INR)
	18,80,000

	GST @ 18% (INR)
	3,38,400

	Total Purchase Order Value (INR)
	22,18,400


5. Payment Terms
Payment against this Purchase Order shall be made in the following milestones, all processed via NEFT/RTGS to the Architect's designated bank account in India Bangalore:
	Milestone
	Trigger
	Percentage
	Amount (INR)

	Advance
	Upon signing of this Purchase Order
	20%
	4,43,680

	Concept Approval
	Buyer's written approval of Concept Design
	15%
	3,32,760

	Schematic Approval
	Buyer's written approval of Schematic Design
	20%
	4,43,680

	Working Drawings Delivered
	Submission of complete drawing set
	25%
	5,54,600

	Statutory Approval Obtained
	BBMP/BDA sanction letter received
	10%
	2,21,840

	Construction Supervision
	Monthly pro-rata during 18-month period
	7%
	1,55,288

	Final Handover
	As-built documentation accepted
	3%
	66,552


6. Terms and Conditions
1. This Purchase Order is governed by the laws of India and shall be interpreted in accordance with the Indian Contract Act, 1872. Any disputes arising from this Purchase Order shall be subject to the exclusive jurisdiction of the competent courts in India Bangalore, Karnataka.
1. The Architect shall hold a valid registration with the Council of Architecture (COA), Government of India, and a valid Karnataka State Architect registration throughout the duration of this engagement. The Architect shall maintain professional indemnity insurance of not less than INR 50,00,000.
1. All architectural drawings, designs, and intellectual property created under this Purchase Order shall become the exclusive property of the Buyer upon full and final payment. The Architect shall not reuse, reproduce, or disclose project-specific designs to any third party without prior written consent.
1. The Architect shall comply with all applicable building by-laws of BBMP, the Karnataka Town and Country Planning Act, 1961, the National Building Code of India, and all environmental clearances mandated for projects in India Bangalore.
1. Any variation or change order to the scope defined in this Purchase Order must be documented in writing and signed by both parties before execution. The Architect shall submit a revised cost estimate for any such variation within five (5) working days.
1. The Architect shall provide a minimum of two (2) design revision cycles at each design phase at no additional cost. Revisions beyond the agreed cycles shall be billed at the Architect's standard hourly rate of INR 3,500 per hour.
1. Payment terms are net thirty (30) days from the date of invoice issuance, provided the corresponding milestone deliverable has been accepted in writing by the Buyer's project team in India Bangalore.
1. The Architect shall not subcontract any portion of the architectural services without prior written approval from the Buyer. Any approved subcontractor shall remain under the Architect's full professional supervision and liability.
1. This Purchase Order shall remain valid for thirty (30) calendar days from the date of issue. If not accepted and signed by the Architect within this period, the Purchase Order shall lapse and must be re-issued.
1. Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to natural disasters, government policy changes affecting construction in India Bangalore, or pandemics, provided written notice is given within 48 hours of the event.
1. The Architect shall maintain complete confidentiality of all project information, site data, and commercial details shared under this Purchase Order, both during and for a period of three (3) years after project completion.
7. Acceptance and Signatures
By signing below, both parties acknowledge and agree to all terms, conditions, and scope of work outlined in this Purchase Order for the engagement of the Architect for the referenced project in India Bangalore.
For and on behalf of the Buyer:
Deccan Urban Development Pvt. Ltd.
Name: Mr. Rajesh Kumar
Designation: Director – Projects
Signature: _________________________
Date: _______________
Place: India Bangalore
For and on behalf of the Architect:
Studio Meridian Architects & Planners
Name: Ms. Ananya Deshpande
Designation: Principal Architect
Signature: _________________________
Date: _______________
Place: India Bangalore
This Purchase Order (No. BLR-ARC-2025-00472) is issued by Deccan Urban Development Pvt. Ltd., India Bangalore, for the engagement of professional Architect services. This document is valid only when signed and stamped by both parties. For queries, contact the Projects Department at +91-80-4112-7788. © 2025 Deccan Urban Development Pvt. Ltd. All rights reserved.
