Purchase Order - Architect Services - Morocco Casablanca
PURCHASE ORDER
Architectural Design & Consulting Services — Morocco Casablanca
Issuing Company
Atlas Horizon Developments SARL
142 Boulevard Mohammed V, 6th Floor
Casablanca 20250, Morocco
RC: 458721 — ICE: 002345678000091
TIN: 40567891
Tel: +212 522-345-678
Email: procurement@atlashorizon.ma
PO No: AHD-2025-0047
Date of Issue: 15 June 2025
Valid Until: 15 July 2025
Project Reference: Casablanca Marina Tower — Phase II
Location: Morocco Casablanca, Ain Diab District
1. Vendor / Architect Information
	Field
	Details

	Architect Firm
	Bureau d'Architecture El Fassi & Partners

	Lead Architect
	Architect Youssef El Fassi, M.Arch, MIAU (Moroccan Institute of Architects)

	Address
	28 Rue Ibnou Sina, Maârif, Casablanca 20100, Morocco

	Professional License
	Order of Architects of Morocco — License No. MA-2003-1187

	ICE
	001987654000042

	Contact
	architect@elfassipartners.ma | +212 522-987-654

	Bank Details
	Bank: Attijariwafa Bank — IBAN: MA64 4002 1010 0312 3456 7890 12


2. Scope of Architectural Services
This Purchase Order is issued by Atlas Horizon Developments SARL to engage the above-named Architect firm for the complete architectural design, planning, and regulatory compliance services for the Casablanca Marina Tower — Phase II project, located in the Ain Diab coastal district of Morocco Casablanca. The Architect shall deliver all services in accordance with the Moroccan Urban Planning Code (Code de l'Urbanisme), the local Casablanca municipal building regulations, and the professional standards established by the Order of Architects of Morocco.
3. Line Items & Pricing
	#
	Description of Architect Service
	Quantity
	Unit (MAD)
	Total (MAD)
	Delivery / Milestone

	1
	Feasibility study and site analysis for the Morocco Casablanca coastal plot (Lot 47, Ain Diab)
	1
	85,000
	85,000
	Within 30 days of PO acceptance

	2
	Conceptual architectural design including massing studies, orientation analysis, and preliminary floor plans for a 28-storey mixed-use tower
	1
	220,000
	220,000
	Within 60 days of PO acceptance

	3
	Detailed architectural drawings (construction set) compliant with Casablanca municipal building permit requirements
	1
	350,000
	350,000
	Within 120 days of PO acceptance

	4
	Interior architectural design for lobby, amenity floors, and residential unit types (A, B, C)
	1
	180,000
	180,000
	Within 150 days of PO acceptance

	5
	Regulatory submission package preparation and coordination with the Casablanca Urban Planning Directorate (Direction de l'Urbanisme)
	1
	95,000
	95,000
	Within 180 days of PO acceptance

	6
	Construction-phase architectural supervision and site visits (minimum 40 site visits over 18 months)
	40
	3,500
	140,000
	Over 18-month construction period

	7
	Final as-built documentation and handover to the Morocco Casablanca municipal authorities
	1
	60,000
	60,000
	Within 30 days of project completion

	Subtotal (MAD)
	1,130,000
	

	VAT (20% — Moroccan standard rate)
	226,000
	

	Grand Total (MAD)
	1,356,000
	


4. Payment Terms
Payment shall be made in Moroccan Dirhams (MAD) via bank transfer to the Architect's designated account. The payment schedule is structured as follows:
	Milestone
	Percentage
	Amount (MAD)
	Trigger

	Advance payment upon signature
	20%
	271,200
	Within 10 business days of PO acceptance

	Conceptual design approval
	25%
	339,000
	Written approval by Atlas Horizon project director

	Construction drawings delivery
	25%
	339,000
	Submission of full construction set

	Building permit obtained
	15%
	203,400
	Issuance of permis de construire by Casablanca municipality

	Construction supervision (monthly)
	10%
	135,600
	Monthly progress reports accepted

	Final handover
	5%
	67,800
	Completion of as-built documentation


5. Terms and Conditions
1. Governing Law: This Purchase Order shall be governed by and interpreted in accordance with the laws of the Kingdom of Morocco, including the Moroccan Civil Code and the specific provisions of the Moroccan Urban Planning Code applicable to the city of Casablanca.
1. Architect's Obligations: The Architect shall ensure all designs comply with the seismic regulations of Morocco (RPS 2011), the Moroccan fire safety code, and the specific zoning regulations of the Ain Diab district in Casablanca. The Architect shall maintain professional liability insurance with a minimum coverage of 5,000,000 MAD throughout the duration of this Purchase Order.
1. Intellectual Property: All architectural drawings, models, and design documents produced under this Purchase Order shall become the exclusive property of Atlas Horizon Developments SARL upon full payment. The Architect retains the right to reference the project in professional portfolios subject to prior written consent.
1. Revisions: The Architect shall include up to three (3) rounds of revisions at each design milestone at no additional cost. Additional revisions beyond this limit shall be billed at 15,000 MAD per day of the Architect's time.
1. Dispute Resolution: Any dispute arising from this Purchase Order shall first be subject to good-faith negotiation. If unresolved within 30 days, the matter shall be referred to the competent commercial court of Casablanca, Morocco.
1. Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to natural disasters, government regulatory changes in Morocco, or civil unrest affecting Casablanca.
1. Confidentiality: The Architect agrees to maintain strict confidentiality regarding all project details, client information, and proprietary data shared in connection with this Purchase Order for a period of five (5) years following project completion.
6. Acceptance and Signatures
By signing below, both parties acknowledge and agree to the terms, conditions, and scope of work outlined in this Purchase Order for the Architectural Services to be delivered in Morocco Casablanca.
For Atlas Horizon Developments SARL (Buyer)
Name: Karim Benjelloun
Title: Chief Procurement Officer
Date: _______________
Signature & Company Stamp
For Bureau d'Architecture El Fassi & Partners (Architect / Vendor)
Name: Youssef El Fassi
Title: Lead Architect, MIAU
Date: _______________
Signature & Company Stamp
This Purchase Order (No. AHD-2025-0047) is valid for a period of thirty (30) calendar days from the date of issue. It is issued in two (2) original copies, one for each party. All communications regarding this Purchase Order shall be directed to the procurement department of Atlas Horizon Developments SARL, Casablanca, Morocco. The Architect is required to confirm acceptance in writing within ten (10) business days of receipt. Failure to confirm within this period shall render this Purchase Order null and void.
