Purchase Order - Architect Services - Russia Moscow
PURCHASE ORDER
Professional Architect Services — Russia Moscow
PO No: RUS-MOW-2025-04871 | Date of Issue: 15 June 2025
Purchasing Party (Buyer)
Company: Strelka Development Group LLC
Address: 12 Tverskaya Street, Building 3, Moscow, Russia Moscow 125009
INN/KPP: 7707083893 / 770701001
Authorized Representative: Dmitry A. Volkov, Chief Procurement Officer
Contact: d.volkov@strelkadev.ru | +7 (495) 620-4411
Supplier Party (Architect Firm)
Company: Bureau 74 Architectural Design Studio
Address: 5 Bolshaya Nikitskaya Street, Moscow, Russia Moscow 125009
INN/KPP: 7710456218 / 771001001
Authorized Representative: Elena S. Morozova, Lead Architect & Director
Contact: e.morozova@bureau74.ru | +7 (495) 240-8832
1. Purchase Order Description
This Purchase Order is issued by Strelka Development Group LLC, a registered entity operating within the jurisdiction of Russia Moscow, to procure the professional services of a licensed Architect and the associated architectural design studio, Bureau 74 Architectural Design Studio. This Purchase Order governs the engagement of the Architect for the complete design, planning, and documentation of a mixed-use residential and commercial complex located in the Presnensky District of Moscow, Russia Moscow. The Architect shall deliver all design phases in strict compliance with the Russian Building Code (GOST R 50670-2000), local Moscow municipal zoning regulations, and the Federal Law No. 384-FZ on Technical Regulation in Construction.
2. Scope of Architect Services
The Architect engaged under this Purchase Order shall perform the following professional services for the project situated in Russia Moscow:
	Item No.
	Description of Architect Service
	Deliverable
	Quantity
	Unit Price (RUB)
	Total (RUB)

	01
	Conceptual Architect Design & Feasibility Study for the mixed-use complex in Russia Moscow
	Concept drawings, massing models, site analysis report
	1
	2,850,000
	2,850,000

	02
	Schematic Design Phase by the Architect — floor plans, elevations, and structural coordination
	Full schematic design package (PDF & DWG)
	1
	4,200,000
	4,200,000

	03
	Detailed Architect Documentation & Construction Drawings compliant with Moscow building permits
	Complete construction drawing set (A1 sheets)
	1
	6,750,000
	6,750,000

	04
	Architect Supervision & Site Visits during construction in Russia Moscow (minimum 24 site inspections)
	Weekly progress reports, punch lists, compliance certificates
	24
	185,000
	4,440,000

	05
	Interior Architect Design for lobby, common areas, and model apartment units
	Interior design package, material schedules, 3D renderings
	1
	3,100,000
	3,100,000

	06
	Landscape Architect Consultation & External Area Design for the Moscow site
	Landscape plan, planting schedule, hardscape details
	1
	1,950,000
	1,950,000

	07
	Permit Application Support & Coordination with Moscow City Architectural Department
	Submitted permit package, revision responses, approval letter
	1
	1,200,000
	1,200,000

	08
	As-Built Documentation & Final Architect Certification upon project completion
	As-built drawing set, final compliance statement
	1
	980,000
	980,000

	TOTAL PURCHASE ORDER VALUE (RUB):
	25,470,000


3. Payment Terms
All payments under this Purchase Order shall be made in Russian Rubles (RUB) via bank transfer to the Architect firm's designated account. The payment schedule is structured as follows:
	Milestone
	Percentage
	Amount (RUB)
	Due Date

	Advance payment upon Purchase Order acceptance
	20%
	5,094,000
	Within 10 business days of signing

	Upon approval of Conceptual Design
	15%
	3,820,500
	Within 15 business days of approval

	Upon delivery of Schematic Design
	20%
	5,094,000
	Within 15 business days of delivery

	Upon delivery of Construction Drawings
	25%
	6,367,500
	Within 15 business days of delivery

	Upon completion of Architect Supervision & As-Built
	20%
	5,094,000
	Within 30 business days of final certification


4. Terms and Conditions
1. Governing Law: This Purchase Order shall be governed by and construed in accordance with the Civil Code of the Russian Federation and all applicable federal and municipal laws of Russia Moscow. Any disputes arising from this Purchase Order shall be resolved by the Arbitration Court of the City of Moscow.
1. Architect Licensing: The Architect and all associated design professionals engaged under this Purchase Order must hold valid licenses issued by the Russian Ministry of Construction and Housing. The Architect firm must maintain professional liability insurance with a minimum coverage of 50,000,000 RUB throughout the duration of the engagement.
1. Intellectual Property: All architectural drawings, designs, models, and documentation produced by the Architect under this Purchase Order shall become the exclusive property of Strelka Development Group LLC upon full payment. The Architect retains the right to display the completed project in professional portfolios with prior written consent from the Buyer.
1. Compliance with Moscow Regulations: The Architect shall ensure that all deliverables comply with the current Moscow City Charter, the Moscow Regional Building Code, and all environmental impact assessment requirements specific to the Russia Moscow jurisdiction. The Architect is responsible for incorporating all feedback from the Moscow City Architectural Department during the permit review process.
1. Timeline: The Architect shall complete all design phases within 14 calendar months from the date of Purchase Order acceptance. Architect supervision shall continue for the full duration of construction, estimated at 22 months. Delays attributable to the Architect shall incur a penalty of 0.05% of the total Purchase Order value per calendar day of delay.
1. Revisions: The Architect shall include up to three (3) rounds of revisions per design phase at no additional cost. Additional revisions requested by the Buyer beyond the included rounds shall be billed at the Architect's standard hourly rate of 12,000 RUB per hour.
1. Force Majeure: Neither party shall be liable for failure to perform obligations under this Purchase Order due to events beyond reasonable control, including but not limited to natural disasters, government sanctions, or changes in Russia Moscow municipal legislation that materially affect project scope.
1. Confidentiality: Both parties agree to maintain strict confidentiality regarding all project details, financial terms of this Purchase Order, and proprietary information exchanged during the Architect engagement. This obligation survives for five (5) years following project completion.
1. Termination: Either party may terminate this Purchase Order with 30 days' written notice. In the event of termination, the Buyer shall pay the Architect for all services rendered and materials procured up to the termination date, as documented in a final Architect progress report.
5. Acceptance and Authorization
This Purchase Order becomes effective upon signature by both authorized representatives. The Architect acknowledges receipt of this Purchase Order and confirms acceptance of all terms, conditions, and scope of work as described herein. The Architect confirms that all services will be performed in accordance with the professional standards of the Russian Union of Architects and the specific regulatory framework of Russia Moscow.
For and on behalf of the Buyer:
Strelka Development Group LLC
Dmitry A. Volkov
Chief Procurement Officer
Date: _______________
For and on behalf of the Architect:
Bureau 74 Architectural Design Studio
Elena S. Morozova
Lead Architect & Director
Date: _______________
Purchase Order No. RUS-MOW-2025-04871 | Issued in Russia Moscow | Page 1 of 1
This document is a legally binding Purchase Order for Architect services. All references to Russia Moscow denote the municipal jurisdiction and regulatory authority applicable to this engagement.
