Purchase Order - Architectural Services - Spain Valencia
PURCHASE ORDER
Architectural Design & Consulting Services — Spain Valencia Region
Purchase Order No.: PO-VAL-2025-04872
Date of Issue: 14 June 2025
Valid Until: 14 September 2025
Project Reference: VAL-ARCH-2025-031
Region: Spain Valencia (Comunidad Valenciana)
Governing Law: Spanish Civil Code & Ley 38/2003
1. Purchasing Entity (Buyer)
Company: Inversiones Turísticas del Turia, S.L.
Address: Avenida del Puerto, 45, 3ª Planta, 46022 Valencia, Spain
VAT (NIF): B-46882319
Contact Person: Mr. Alejandro Ferrer, Director of Procurement
Email: procurement@inversionesturia.es
Telephone: +34 963 554 210
2. Supplier (Architect & Design Firm)
Company: Estudio Arquitectónico Levante, S.L.P.
Address: Calle de la Paz, 12, Bajo, 46003 Valencia, Spain
VAT (NIF): B-46119074
Lead Architect: Arq. María Dolores Sanchís (Colegio Oficial de Arquitectos de Valencia, Nº 12.847)
Email: info@estudiolevante.es
Telephone: +34 960 227 843
3. Description of Architectural Services
This Purchase Order is issued by Inversiones Turísticas del Turia, S.L. to Estudio Arquitectónico Levante, S.L.P. for the provision of comprehensive architectural design, planning, and consulting services for the development of a mixed-use residential and commercial complex located in the Ruzafa district of Valencia, Spain. The Architect shall be responsible for all phases of design, from initial concept development through to final construction documentation, in full compliance with the urban planning regulations of the Ayuntamiento de Valencia and the applicable building codes of the Comunidad Valenciana.
4. Scope of Work & Line Items
	Item
	Description
	Phase
	Duration
	Amount (EUR)

	01
	Initial feasibility study, site analysis, and conceptual design for the mixed-use complex in Ruzafa, Valencia
	Concept
	8 weeks
	18,500.00

	02
	Development of preliminary architectural drawings, 3D visualisations, and material specifications
	Pre-Design
	10 weeks
	32,000.00

	03
	Full construction documentation set, structural coordination, MEP integration, and compliance with Valencia municipal building permits
	Design Development
	14 weeks
	54,750.00

	04
	Submission and management of the building permit application (Licencia de Obra Mayor) with the Ayuntamiento de Valencia
	Permitting
	6 weeks
	12,300.00

	05
	Construction-phase architectural supervision, site inspections, and progress reporting (minimum 4 site visits per month in Valencia)
	Construction
	18 months
	78,400.00

	06
	Final as-built documentation, handover dossier, and post-occupancy evaluation
	Close-Out
	6 weeks
	9,850.00

	Subtotal
	205,800.00

	VAT (IVA) at 21% — Spain Valencia
	43,218.00

	Total Purchase Order Value
	249,018.00


5. Payment Terms
Payment shall be made in accordance with the following schedule, invoiced by the Architect upon completion of each phase and approved by the Buyer's project manager:
· Advance Payment: 15% of the total Purchase Order value (EUR 37,352.70) within 15 business days of the signed contract, to be deposited into the Architect's designated bank account in Spain.
· Progress Payments: 70% of the total value shall be disbursed in monthly instalments corresponding to the completion of each phase as outlined in Section 4, subject to written acceptance by the Buyer.
· Retention: 10% of each phase payment shall be retained by the Buyer and released within 30 days of final project completion and handover of all as-built documentation.
· Final Payment: The remaining 5% shall be paid within 21 days of the post-occupancy evaluation being accepted in writing.
· All payments shall be made via bank transfer (SEPA) to the account details provided by Estudio Arquitectónico Levante, S.L.P. Invoices must reference this Purchase Order number (PO-VAL-2025-04872) and comply with the electronic invoicing requirements established under Spanish Royal Decree 1058/2022.
6. Terms and Conditions
1. This Purchase Order and all associated services shall be governed by and construed in accordance with the laws of Spain, specifically the Spanish Civil Code, the Ley 38/2003 General Law on Public Contracts (where applicable), and the professional regulations of the Colegio Oficial de Arquitectos de Valencia.
1. The Architect warrants that all design work shall comply with the vigente Plan General de Ordenación Urbana de Valencia, the technical building regulations (CTE), and all environmental and accessibility requirements applicable in the Comunidad Valenciana.
1. The Architect shall maintain professional indemnity insurance with a minimum coverage of EUR 1,000,000 per claim, valid throughout the duration of this Purchase Order and for a further five years following project completion.
1. Any changes to the scope of work must be documented in a written variation order signed by both parties. No additional work shall be performed without prior written authorisation under this Purchase Order.
1. The Architect shall deliver all project files in both PDF and editable CAD/BIM formats (Revit or equivalent) to the Buyer upon completion of each phase.
1. Confidentiality: Both parties agree to treat all project information, site data, and commercial terms as strictly confidential in accordance with the Spanish Data Protection Act (LOPDGDD 3/2018) and the EU General Data Protection Regulation (GDPR).
1. Disputes arising from this Purchase Order shall first be subject to mediation in Valencia, Spain. Should mediation fail, the matter shall be referred to the competent courts of Valencia, Spain, as the exclusive jurisdiction.
1. The Architect shall not subcontract any portion of the architectural services without the prior written consent of the Buyer, as stipulated in this Purchase Order.
1. Force majeure events, including but not limited to natural disasters affecting the Valencia region, shall be addressed in accordance with Article 1105 of the Spanish Civil Code.
7. Acceptance & Signatures
By signing below, both parties acknowledge and agree to all terms, conditions, and obligations set forth in this Purchase Order for the architectural services to be delivered in Spain Valencia.
For and on behalf of the Buyer:
Inversiones Turísticas del Turia, S.L.
Name: Alejandro Ferrer
Title: Director of Procurement
Signature: _________________________
Date: _________________________
For and on behalf of the Architect:
Estudio Arquitectónico Levante, S.L.P.
Name: Arq. María Dolores Sanchís
Title: Lead Architect & Managing Partner
Signature: _________________________
Date: _________________________
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