Purchase Order - Architect Services - Sri Lanka Colombo
PURCHASE ORDER
Architectural Design & Consultancy Services
Sri Lanka Colombo
Issued By (Buyer)
Colombo Urban Development Corporation (Pvt) Ltd.
No. 42, Galle Road, Colombo 03
Sri Lanka
Tel: +94 11 234 5678
Email: procurement@colombourban.lk
Registration No: C03/2019/4521
Issued To (Vendor / Architect)
Mr. Nimal Perera, ARIASL
Perera & Associates Architects
No. 18, Temple Road, Colombo 07
Sri Lanka Colombo
Tel: +94 11 456 7890
Email: nimal@pereraarchitects.lk
Architect Registration No: ARIASL/2005/0892
	Purchase Order No:
	PO/CUD/2025/0047
	Date of Issue:
	15 June 2025

	Project Reference:
	CUD-RES-2025-012
	Delivery/Completion:
	30 November 2025

	Project Location:
	Colombo 05, Sri Lanka
	Payment Terms:
	Net 30 Days

	Currency:
	Sri Lankan Rupees (LKR)
	Validity:
	30 Days from Issue Date


Description of Architect Services
	No.
	Service Description
	Phase
	Duration
	Amount (LKR)

	1
	Pre-design feasibility study, site analysis, and concept development for a 12-storey mixed-use residential and commercial building in Colombo 05, Sri Lanka. The Architect shall conduct a thorough assessment of the site, local planning regulations of the Colombo Municipal Council, and environmental impact considerations specific to the Sri Lanka Colombo urban context.
	Phase I – Concept
	6 Weeks
	1,850,000.00

	2
	Development of detailed architectural drawings including floor plans, elevations, sections, and 3D visualisations. The Architect shall ensure compliance with the Sri Lanka Building Code, National Building Regulations, and all applicable standards set by the Department of Building Construction, Sri Lanka Colombo.
	Phase II – Design Development
	10 Weeks
	3,200,000.00

	3
	Production of full construction documentation, structural coordination drawings, MEP (Mechanical, Electrical, Plumbing) coordination, and specification schedules. The Architect shall coordinate with all specialist consultants and submit all documentation to the relevant Sri Lanka Colombo authorities for building permit approval.
	Phase III – Construction Documents
	12 Weeks
	4,500,000.00

	4
	Construction phase supervision, site inspections (minimum twice weekly), progress reporting, and resolution of design queries. The Architect shall maintain a permanent presence at the Sri Lanka Colombo project site during critical construction milestones and provide written reports to the Buyer within 48 hours of each inspection.
	Phase IV – Construction Supervision
	26 Weeks
	5,750,000.00

	5
	Final as-built documentation, snag list preparation, handover documentation, and warranty period support (12 months post-completion). The Architect shall ensure all final records are archived in accordance with Sri Lanka Colombo municipal record-keeping requirements.
	Phase V – Handover & Warranty
	14 Weeks
	1,200,000.00

	TOTAL CONTRACT VALUE (Inclusive of all applicable taxes)
	16,500,000.00


Terms and Conditions
1. Scope of Work: This Purchase Order constitutes a binding agreement between Colombo Urban Development Corporation (Pvt) Ltd. and the named Architect for the provision of comprehensive architectural design and consultancy services for the project located in Sri Lanka Colombo. The Architect shall perform all duties in accordance with the professional standards of the Architectural Registration Board of Sri Lanka and the Institute of Architects of Sri Lanka.
2. Payment Schedule: Payments shall be made in accordance with the following milestones: 15% upon execution of this Purchase Order, 20% upon completion of Phase I, 20% upon completion of Phase II, 25% upon completion of Phase III, 15% upon completion of Phase IV, and 5% upon final handover and acceptance. All payments shall be made via bank transfer to the Architect's designated account in Sri Lanka Colombo within 30 days of receipt of a valid invoice.
3. Intellectual Property: All drawings, designs, models, and documentation produced by the Architect under this Purchase Order shall become the exclusive property of the Buyer upon full payment. The Architect shall not reuse, reproduce, or disclose any project-specific information pertaining to the Sri Lanka Colombo site without prior written consent.
4. Compliance and Permits: The Architect shall be solely responsible for ensuring that all design submissions comply with the Town and Country Planning Act, the National Building Regulations, and all local by-laws of the Colombo Municipal Council. The Architect shall manage all interactions with Sri Lanka Colombo planning authorities and obtain necessary building permits on behalf of the Buyer.
5. Insurance and Liability: The Architect shall maintain professional indemnity insurance with a minimum cover of LKR 50,000,000 throughout the duration of this Purchase Order. The Architect shall be liable for any design errors or omissions that result in structural failure, code violations, or financial loss to the Buyer.
6. Termination: Either party may terminate this Purchase Order with 30 days written notice. In the event of termination, the Architect shall be compensated for all work completed and documented up to the date of termination, as assessed by an independent professional appointed by the Sri Lanka Colombo arbitration panel.
7. Dispute Resolution: Any disputes arising from this Purchase Order shall be resolved through mediation in Sri Lanka Colombo in accordance with the Arbitration Act of Sri Lanka. The courts of Colombo, Sri Lanka shall have exclusive jurisdiction.
8. Force Majeure: Neither party shall be liable for delays caused by natural disasters, government-imposed restrictions, or other events beyond reasonable control, as commonly experienced in the Sri Lanka Colombo region including monsoon-related construction delays.
For and on behalf of the Buyer:
Colombo Urban Development Corporation (Pvt) Ltd.
Name: Mr. R. Jayawardena
Title: Chief Procurement Officer
Signature: _________________________
Date: _________________________
For and on behalf of the Architect:
Perera & Associates Architects, Sri Lanka Colombo
Name: Mr. Nimal Perera, ARIASL
Title: Principal Architect
Signature: _________________________
Date: _________________________
This Purchase Order is issued in accordance with the procurement policies of Colombo Urban Development Corporation (Pvt) Ltd. and the professional practice standards of the Architectural Registration Board of Sri Lanka. This document is valid only for the project located in Sri Lanka Colombo and shall not be transferred or assigned to any third party without written consent of both parties. Document Reference: PO/CUD/2025/0047 | Page 1 of 1
