# Purchase Order - Business Consultant Services - Italy Milan

# PURCHASE ORDER

Business Consultant Professional Services — Italy Milan

Document Reference: PO-ITM-2025-04782

### BUYER / REQUIRING DEPARTMENT

Company: Lombardi Industrial Group S.p.A.

Address: Via Torino 34, 20123 Milan, Italy

VAT Number (P.IVA): IT02345678901

Contact: Dr. Elena Marchetti, Procurement Director

Email: procurement@lombardigroup.it

Phone: +39 02 8765 4321

### SUPPLIER / BUSINESS CONSULTANT

Firm: Strategia & Visione Consulting S.r.l.

Address: Piazza Gae Aulenti 5, 20154 Milan, Italy

VAT Number (P.IVA): IT09876543210

Contact: Ing. Marco Bellini, Lead Business Consultant

Email: m.bellini@strategiavisione.it

Phone: +39 02 4567 8910

| Purchase Order Number: | PO-ITM-2025-04782 |
| --- | --- |
| Date of Issue: | 14 June 2025 |
| Required Start Date: | 1 July 2025 |
| Project Duration: | 6 months (1 July 2025 – 31 December 2025) |
| Place of Performance: | Milan, Italy (Primary Office: Via Torino 34, 20123 Milan) |
| Currency: | Euro (EUR) |
| Governing Law: | Italian Civil Code (Codice Civile) — Republic of Italy |
| Jurisdiction: | Court of Milan, Italy |

## 1. DESCRIPTION OF SERVICES — BUSINESS CONSULTANT ENGAGEMENT

This Purchase Order is issued by Lombardi Industrial Group S.p.A. to formally engage Strategia & Visione Consulting S.r.l. to provide comprehensive Business Consultant services. The engagement is specifically tailored to the operational, strategic, and regulatory environment of Italy Milan, ensuring that all advisory deliverables align with local market conditions, Italian commercial law, and the specific economic landscape of the Milan metropolitan area. The Business Consultant shall deliver the following scope of work:

| Ref. | Service Description | Deliverable | Duration | Fee (EUR) |
| --- | --- | --- | --- | --- |
| 1.1 | Strategic Business Planning & Market Analysis for the Milan industrial sector | Comprehensive strategic report with SWOT analysis | Months 1–2 | €18,500.00 |
| 1.2 | Operational Process Optimization & Lean Implementation Advisory | Process mapping documentation and implementation roadmap | Months 2–4 | €22,000.00 |
| 1.3 | Regulatory Compliance Review (Italian & EU Business Law, Milan Chamber of Commerce requirements) | Compliance audit report and corrective action plan | Months 3–5 | €12,800.00 |
| 1.4 | Financial Restructuring & Cost Optimization Strategy | Financial model and restructuring proposal | Months 4–6 | €15,200.00 |
| 1.5 | Change Management & Executive Training Workshops (conducted in Milan office) | 4 workshops (12 hours each) with participant materials | Months 5–6 | €9,500.00 |
| 1.6 | Final Integration Report & 90-Day Post-Engagement Support | Executive summary, KPI dashboard, and remote support | Month 6 + 90 days | €7,000.00 |

Subtotal: €85,000.00

VAT (IVA 22%): €18,700.00

Grand Total: €103,700.00

## 2. TERMS AND CONDITIONS

- Scope & Location: All services under this Purchase Order shall be performed primarily at the Buyer's premises located in Milan, Italy, or at mutually agreed locations within the Milan metropolitan area. The Business Consultant acknowledges and agrees to comply with all applicable Italian labor regulations, data protection laws (GDPR and Italian D.Lgs. 196/2003), and local business practices specific to Italy Milan.

- Payment Terms: Payment shall be made in three equal installments of €34,566.67 (including VAT) via bank transfer (bonifico bancario) to the account specified by the Business Consultant. The first installment is due upon execution of this Purchase Order, the second upon completion of Month 3 deliverables, and the third upon final acceptance of all deliverables. Payment terms are net 30 days from invoice date in accordance with Italian commercial practice.

- Confidentiality: The Business Consultant shall maintain strict confidentiality over all proprietary information, trade secrets, and business data of Lombardi Industrial Group S.p.A. This obligation survives the termination of this Purchase Order for a period of five (5) years, in compliance with Italian confidentiality law.

- Intellectual Property: All reports, analyses, models, and deliverables produced under this Purchase Order shall become the exclusive property of the Buyer upon full payment. The Business Consultant retains the right to use anonymized, aggregated findings for internal methodology improvement only.

- Termination: Either party may terminate this Purchase Order with thirty (30) days' written notice. In the event of termination, the Business Consultant shall be compensated for all services rendered up to the termination date, and all work-in-progress deliverables shall be handed over.

- Dispute Resolution: Any dispute arising from this Purchase Order shall be resolved through amicable negotiation. Failing resolution within 30 days, the matter shall be submitted to the exclusive jurisdiction of the Court of Milan, Italy, in accordance with Italian procedural law.

- Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to natural disasters, government mandates, or public health emergencies affecting the Milan region, as defined under Article 1218 of the Italian Civil Code.

- Anti-Corruption & Compliance: The Business Consultant warrants compliance with all Italian anti-corruption legislation (D.Lgs. 231/2001) and confirms that no part of the fees under this Purchase Order shall be used for improper payments or inducements.

## 3. ACCEPTANCE AND AUTHORIZATION

By signing below, both parties acknowledge and agree to all terms, conditions, and service descriptions outlined in this Purchase Order for the engagement of the Business Consultant in Italy Milan. This document constitutes a binding commercial agreement under Italian law.

For the Buyer:
Dr. Elena Marchetti
Procurement Director, Lombardi Industrial Group S.p.A.
Date: _______________

For the Business Consultant:
Ing. Marco Bellini
Lead Business Consultant, Strategia & Visione Consulting S.r.l.
Date: _______________

This Purchase Order (PO-ITM-2025-04782) is issued in Milan, Italy, and governed by the laws of the Republic of Italy. All communications regarding this Business Consultant engagement should be directed to the Procurement Department, Lombardi Industrial Group S.p.A., Via Torino 34, 20123 Milan, Italy. This document is valid for a period of 60 days from the date of issue. © 2025 Lombardi Industrial Group S.p.A. — All Rights Reserved.