Purchase Order - Carpenter Services - China Shanghai
PURCHASE ORDER
Shanghai Construction & Interiors Ltd.
888 Century Avenue, Pudong New Area, China Shanghai, 200120
Tel: +86-21-5888-6600 | Email: procurement@shci-interiors.cn
Purchase Order No.: PO-2025-SH-0472
Date of Issue: 15 June 2025
Required Completion Date: 30 August 2025
Project Reference: SH-INT-2025-114
Payment Terms: Net 30 Days
Currency: Chinese Yuan (CNY / RMB)
1. Parties Involved
	Role
	Name / Entity
	Address & Contact

	Buyer (Purchasing Entity)
	Shanghai Construction & Interiors Ltd.
	888 Century Avenue, Pudong New Area, China Shanghai, 200120, P.R. China
Attn: Mr. Wei Zhang, Procurement Director
Email: w.zhang@shci-interiors.cn

	Supplier (Service Provider)
	Golden Oak Carpenter Workshop Co., Ltd.
	156 Hongqiao Road, Xuhui District, China Shanghai, 200030, P.R. China
Attn: Ms. Lin Fang, Operations Manager
Email: operations@goldenoak-carpenter.cn


2. Description of Purchase Order Scope
This Purchase Order is issued by Shanghai Construction & Interiors Ltd. to Golden Oak Carpenter Workshop Co., Ltd. for the procurement of professional Carpenter services, materials, and craftsmanship required for the interior woodwork and custom furniture installation at the Shanghai International Trade Center, located in the Pudong district of China Shanghai. The scope of work under this Purchase Order encompasses the design, fabrication, and on-site installation of hardwood paneling, custom cabinetry, built-in shelving units, decorative mouldings, and a grand entrance reception desk. All work shall be executed in strict compliance with the national building codes of the People's Republic of China and the specific architectural specifications outlined in Drawing Set SH-INT-2025-114-A through F.
The selected Carpenter team, led by Master Carpenter Chen Guo (25 years of experience in traditional and modern joinery), shall be stationed at the project site in China Shanghai for the duration of the contract. The Carpenter crew shall consist of no fewer than twelve (12) skilled tradespeople, including three senior carpenters, five intermediate carpenters, two apprentices, and two finishing specialists. All personnel must hold valid Chinese work permits and comply with local labor regulations in China Shanghai.
3. Line Items and Pricing
	No.
	Description of Carpenter Services / Materials
	Qty
	Unit (CNY)
	Total (CNY)
	Delivery / Execution

	1
	Custom walnut hardwood wall paneling – design, fabrication, and installation (Carpenter labor + materials)
	1,200 m²
	¥ 1,850.00
	¥ 2,220,000.00
	Weeks 1–6

	2
	Built-in oak cabinetry for executive offices (Carpenter craftsmanship, 48 units)
	48 units
	¥ 12,500.00
	¥ 600,000.00
	Weeks 3–8

	3
	Grand entrance reception desk – solid mahogany with brass inlay (Master Carpenter lead project)
	1 unit
	¥ 185,000.00
	¥ 185,000.00
	Weeks 5–9

	4
	Decorative ceiling mouldings and crown trim – all floors (Carpenter installation)
	3,400 lm
	¥ 220.00
	¥ 748,000.00
	Weeks 7–10

	5
	On-site Carpenter supervision, quality inspection, and project management (full duration)
	12 weeks
	¥ 45,000.00
	¥ 540,000.00
	Weeks 1–12

	6
	Finishing, sanding, and eco-friendly lacquer application (Carpenter finishing team)
	1,200 m²
	¥ 380.00
	¥ 456,000.00
	Weeks 9–12

	SUBTOTAL
	¥ 4,749,000.00
	

	VAT (13%)
	¥ 617,370.00
	

	GRAND TOTAL (CNY)
	¥ 5,366,370.00
	


4. Terms and Conditions
1. Acceptance: This Purchase Order becomes a binding contract upon written acceptance by the Supplier within five (5) business days of the date of issue. The Supplier shall return a signed copy of this Purchase Order to the Buyer's procurement office in China Shanghai.
1. Performance: The Carpenter team shall commence work on-site no later than 1 July 2025 and shall complete all deliverables by 30 August 2025. Any delay beyond the stipulated completion date shall incur a penalty of 0.5% of the total Purchase Order value per calendar day of delay, capped at 10%.
1. Quality Standards: All woodwork and Carpenter craftsmanship shall conform to the GB/T 3324-2017 national standard for wooden furniture and the project-specific tolerances (±1.5 mm for panel joints, ±0.5 mm for moulding profiles). The Buyer reserves the right to reject any work that does not meet these specifications.
1. Materials: All hardwood materials (walnut, oak, mahogany) shall be FSC-certified and sourced from approved suppliers registered in China Shanghai. The Carpenter workshop shall provide material traceability documentation upon request.
1. Payment Schedule: 30% advance payment upon Purchase Order acceptance; 40% upon completion of wall paneling and cabinetry (interim milestone inspection); 25% upon completion of all installation work; 5% final retention released 60 days after final acceptance and handover.
1. Insurance and Liability: The Supplier (Carpenter workshop) shall maintain comprehensive liability insurance of no less than ¥ 10,000,000 covering all personnel and equipment on-site in China Shanghai. The Supplier assumes full responsibility for any damage to existing structures or third-party property caused by the Carpenter crew.
1. Health, Safety, and Compliance: The Carpenter team shall adhere to all occupational safety regulations enforced by the Shanghai Municipal Housing and Urban-Rural Development Commission. Daily safety briefings and proper PPE (respiratory masks, safety glasses, hearing protection) are mandatory.
1. Dispute Resolution: Any disputes arising from this Purchase Order shall first be resolved through good-faith negotiation. If unresolved within thirty (30) days, the matter shall be submitted to arbitration under the Shanghai Arbitration Commission in accordance with its rules of procedure.
1. Governing Law: This Purchase Order shall be governed by and construed in accordance with the laws of the People's Republic of China, with jurisdiction vested in the competent courts of China Shanghai.
1. Confidentiality: Both parties agree to maintain strict confidentiality regarding the project specifications, architectural drawings, and commercial terms contained in this Purchase Order. No information shall be disclosed to third parties without prior written consent.
5. Authorisation and Signatures
For and on behalf of the Buyer:
Shanghai Construction & Interiors Ltd.
Name: Wei Zhang
Title: Procurement Director
Signature: ___________________________
Date: 15 June 2025
For and on behalf of the Supplier:
Golden Oak Carpenter Workshop Co., Ltd.
Name: Lin Fang
Title: Operations Manager
Signature: ___________________________
Date: _______________
This Purchase Order (PO-2025-SH-0472) is issued for Carpenter services in China Shanghai. This document is valid for acceptance until 22 June 2025. Unauthorized reproduction or distribution is prohibited. © 2025 Shanghai Construction & Interiors Ltd. All rights reserved.
