Purchase Order - Chemical Engineer Services - United Arab Emirates Dubai
PURCHASE ORDER
Purchase Order No.: PO-2025-DXB-CE-0472
Date of Issue: 14 June 2025
Valid Until: 14 July 2025
Project Reference: DXB-CE-2025-0091
Location: United Arab Emirates Dubai
Classification: Professional Services – Engineering
1. Purchasing Party (Buyer)
	Field
	Details

	Company Name
	Al Noor Industrial Solutions LLC

	Trade License No.
	DL-2019-4487213

	Address
	Office 1204, Level 12, Al Futtaim Tower, Sheikh Zayed Road, United Arab Emirates Dubai, 00000

	TRN (Tax Registration Number)
	100212345600003

	Contact Person
	Mr. Khalid Al Mansoori – Procurement Director

	Email / Phone
	procurement@alnoorindustrial.ae / +971 4 555 8821


2. Supplier / Service Provider (Seller)
	Field
	Details

	Company Name
	Meridian Engineering & Technical Consultancy FZ-LLC

	Trade License No.
	DL-2021-7731056

	Address
	Unit 34, Building 7, Dubai Internet City, United Arab Emirates Dubai, 00000

	TRN (Tax Registration Number)
	100398765400003

	Contact Person
	Dr. Sarah Al Farsi – Managing Director

	Email / Phone
	contracts@meridianeng.ae / +971 4 330 6644


3. Scope of Purchase – Chemical Engineer Professional Services
This Purchase Order is issued by Al Noor Industrial Solutions LLC for the engagement of a qualified Chemical Engineer to provide specialized process design, safety assessment, and operational optimization services for the buyer's petrochemical processing facility located in the Jebel Ali Free Zone, United Arab Emirates Dubai. The Chemical Engineer shall be responsible for the following deliverables as outlined in the line items below.
4. Line Items
	Item No.
	Description of Service / Deliverable
	Quantity
	Unit
	Unit Price (AED)
	Total (AED)

	01
	Engagement of a Senior Chemical Engineer (minimum 12 years post-qualification experience, registered with the UAE Council of Engineers) for process flow diagram (PFD) and piping and instrumentation diagram (P&ID) design of a new ethylene glycol production unit.
	1
	Professional
	45,000.00
	45,000.00

	02
	Chemical Engineer-led Hazard and Operability (HAZOP) study for the existing reactor train, including preparation of a comprehensive risk register and mitigation action plan compliant with UAE Federal Law No. 3 of 2009 on Occupational Safety and Health.
	1
	Study
	38,500.00
	38,500.00

	03
	Thermodynamic simulation and heat integration analysis performed by the assigned Chemical Engineer using Aspen HYSYS, covering the distillation column network and waste-heat recovery system.
	1
	Analysis
	27,000.00
	27,000.00

	04
	On-site supervision and commissioning support by the Chemical Engineer at the Jebel Ali facility, United Arab Emirates Dubai, for a period of 20 working days during the start-up phase of the new unit.
	20
	Days
	2,200.00
	44,000.00

	05
	Preparation of a detailed Chemical Process Safety Management (PSM) manual and operator training curriculum authored and reviewed by the Chemical Engineer, aligned with OSHA 29 CFR 1910.119 and UAE Ministry of Energy and Infrastructure guidelines.
	1
	Manual
	22,000.00
	22,000.00

	06
	Monthly progress reporting and technical liaison between the Chemical Engineer and the buyer's project management office, including attendance at bi-weekly coordination meetings in United Arab Emirates Dubai.
	6
	Months
	3,500.00
	21,000.00

	Subtotal
	197,500.00

	VAT (5% – UAE Standard Rate)
	9,875.00

	Grand Total (AED)
	207,375.00


5. Payment Terms
Payment shall be made in United Arab Emirates Dirhams (AED) via bank transfer to the supplier's designated account. The schedule is as follows:
· 30% Advance Payment: AED 62,212.50 (inclusive of VAT) within 10 business days of acceptance of this Purchase Order.
· 40% Milestone Payment: AED 82,950.00 (inclusive of VAT) upon successful delivery and approval of the PFD, P&ID, and HAZOP study deliverables.
· 30% Final Payment: AED 62,212.50 (inclusive of VAT) within 15 business days of completion of commissioning support and submission of the PSM manual.
All invoices must reference this Purchase Order number (PO-2025-DXB-CE-0472) and include the supplier's TRN for VAT compliance under the UAE Federal Decree-Law No. 8 of 2017 on Value Added Tax.
6. Delivery and Performance Schedule
	Milestone
	Target Date
	Location

	Chemical Engineer mobilization and site familiarization
	23 June 2025
	Jebel Ali Free Zone, United Arab Emirates Dubai

	Submission of PFD and P&ID package
	15 August 2025
	United Arab Emirates Dubai

	HAZOP study workshop and report
	30 September 2025
	United Arab Emirates Dubai

	Thermodynamic simulation deliverable
	15 October 2025
	United Arab Emirates Dubai

	Commissioning support (20 days)
	1 November – 20 November 2025
	Jebel Ali Free Zone, United Arab Emirates Dubai

	PSM manual and training curriculum handover
	15 December 2025
	United Arab Emirates Dubai


7. Terms and Conditions
1. This Purchase Order is governed by the laws of the United Arab Emirates and the specific laws and regulations of the Emirate of Dubai. Any disputes arising from this Purchase Order shall be subject to the exclusive jurisdiction of the Dubai Courts.
1. The Chemical Engineer engaged under this Purchase Order must hold a valid professional registration with the UAE Council of Engineers and a current professional indemnity insurance certificate with a minimum coverage of AED 5,000,000.
1. All work performed under this Purchase Order shall comply with the UAE Federal Law No. 3 of 2009 (Occupational Safety and Health), the Dubai Municipality environmental regulations, and the relevant standards of the American Society of Mechanical Engineers (ASME) and the American Petroleum Institute (API).
1. The supplier shall not subcontract any portion of the Chemical Engineer services without prior written consent from the buyer. Any approved subcontractor must meet the same qualification and insurance requirements.
1. Intellectual property rights in all deliverables produced under this Purchase Order shall vest exclusively in the buyer upon full payment. The Chemical Engineer and the supplier retain no ownership or licensing rights over the final designs, reports, and manuals.
1. Confidentiality: Both parties agree to maintain strict confidentiality of all technical data, process parameters, and commercial information exchanged in connection with this Purchase Order. This obligation survives termination for a period of five (5) years.
1. Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to natural disasters, government sanctions, or public health emergencies declared in the United Arab Emirates Dubai.
1. Termination: Either party may terminate this Purchase Order with 30 days' written notice. In the event of termination, the buyer shall pay for all services rendered up to the termination date at the rates specified in this Purchase Order.
1. Warranty: The supplier warrants that all deliverables produced by the Chemical Engineer shall be free from material defects in design and analysis for a period of 12 months from the date of final acceptance.
8. Acceptance and Authorization
By signing below, both parties acknowledge and agree to all terms, conditions, and specifications set forth in this Purchase Order for the engagement of the Chemical Engineer in United Arab Emirates Dubai.
For and on behalf of the Buyer:
Al Noor Industrial Solutions LLC
Name: ___________________________
Title: Procurement Director
Signature: _________________________
Date: _____________________________
Company Stamp:
For and on behalf of the Supplier:
Meridian Engineering & Technical Consultancy FZ-LLC
Name: ___________________________
Title: Managing Director
Signature: _________________________
Date: _____________________________
Company Stamp:
— End of Purchase Order PO-2025-DXB-CE-0472 —
