Purchase Order - Curriculum Developer - Indonesia Jakarta
PO-2025-JKT-0047
Date: 15 June 2025
Valid Until: 15 September 2025
PURCHASE ORDER
Curriculum Developer Services — Indonesia Jakarta Region
1. Parties Involved
Buyer (Purchasing Entity):
Nusantara Educational Solutions PT
Address: Menara Edukasi, 12th Floor, Jl. Jend. Sudirman Kav. 45
Jakarta Selatan, Indonesia Jakarta 12190
Tax ID (NPWP): 02.345.678.9-011.000
Contact: procurement@nusantara-edu.co.id
Phone: +62-21-5555-8901
Vendor / Supplier (Curriculum Developer):
Arus Pendidikan Kreatif CV
Address: Gedung Inovasi, 5th Floor, Jl. Gatot Subroto Kav. 28
Jakarta Pusat, Indonesia Jakarta 10270
Tax ID (NPWP): 09.876.543.2-022.000
Contact: sales@aruspendidikan.id
Phone: +62-21-7777-4321
2. Scope of Purchase — Curriculum Developer Engagement
This Purchase Order is issued by Nusantara Educational Solutions PT, headquartered in Indonesia Jakarta, to formally engage the services of Arus Pendidikan Kreatif CV as a Curriculum Developer for the design, development, and delivery of a comprehensive K-12 curriculum framework. The Curriculum Developer shall produce all instructional materials, assessment instruments, teacher guides, and digital learning modules in alignment with the Indonesian national education standards (Kurikulum Merdeka) as mandated by the Ministry of Education, Culture, Research, and Technology of the Republic of Indonesia. All deliverables must be localized for the Indonesia Jakarta metropolitan context, incorporating regional cultural references, Bahasa Indonesia as the primary instructional language, and English as a secondary language of instruction for international-track programs.
3. Line Items & Pricing
	No.
	Description of Curriculum Developer Deliverable
	Quantity
	Unit
	Unit Price (IDR)
	Total (IDR)

	1
	Curriculum Developer — Design & Development of Grade 1–6 Elementary Curriculum Framework (Bahasa Indonesia, Math, Science, Social Studies)
	1
	Project
	485,000,000
	485,000,000

	2
	Curriculum Developer — Design & Development of Grade 7–9 Junior High Curriculum Framework (including STEM integration)
	1
	Project
	520,000,000
	520,000,000

	3
	Curriculum Developer — Design & Development of Grade 10–12 Senior High Curriculum Framework (including vocational pathways)
	1
	Project
	560,000,000
	560,000,000

	4
	Curriculum Developer — Digital Learning Modules & Interactive Assessments (LMS-compatible, Jakarta-specific content)
	120
	Modules
	8,500,000
	1,020,000,000

	5
	Curriculum Developer — Teacher Training Manuals & Professional Development Workshops (4 sessions in Indonesia Jakarta)
	4
	Sessions
	45,000,000
	180,000,000

	6
	Curriculum Developer — Ongoing Revision, QA & Annual Update Service (12-month retainer)
	1
	Year
	275,000,000
	275,000,000

	Subtotal
	3,040,000,000

	VAT (PPN) 11%
	334,400,000

	GRAND TOTAL (IDR)
	3,374,400,000


4. Delivery Schedule & Milestones
	Milestone
	Curriculum Developer Responsibility
	Due Date
	Location

	M1
	Needs assessment & curriculum mapping workshop
	30 July 2025
	Indonesia Jakarta (Buyer HQ)

	M2
	Delivery of Elementary & Junior High curriculum drafts
	30 September 2025
	Indonesia Jakarta

	M3
	Delivery of Senior High curriculum & digital modules
	30 November 2025
	Indonesia Jakarta

	M4
	Teacher training workshops (4 sessions)
	31 January 2026
	Indonesia Jakarta

	M5
	Final QA, revision & handover of all deliverables
	28 February 2026
	Indonesia Jakarta


5. Payment Terms
Payment for this Purchase Order shall be made in four (4) installments via bank transfer to the Curriculum Developer's designated account, subject to acceptance of each milestone deliverable by the Buyer's Quality Assurance team in Indonesia Jakarta:
Installment 1: 30% (IDR 1,012,320,000) upon signing of this Purchase Order and commencement of work.
Installment 2: 30% (IDR 1,012,320,000) upon acceptance of Milestone M2.
Installment 3: 25% (IDR 843,600,000) upon acceptance of Milestone M3.
Installment 4: 15% (IDR 506,160,000) upon final acceptance of Milestone M5 and completion of the annual retainer period.
All payments are subject to a 30-day net payment cycle from the date of invoice issuance. Late payments shall incur a penalty of 2% per month as stipulated under Indonesian commercial law. The Curriculum Developer must issue a proper tax invoice (faktur pajak) for each installment in compliance with the Directorate General of Taxes regulations applicable in Indonesia Jakarta.
6. Terms & Conditions
1. This Purchase Order constitutes a binding agreement between the Buyer and the Curriculum Developer for the scope of work described herein. Any modifications must be documented in a written change order signed by both parties.
1. The Curriculum Developer warrants that all curriculum materials, digital modules, and training content are original works free from intellectual property infringement. All deliverables shall be registered with the relevant Indonesian copyright authority (DJKI) in the name of the Buyer.
1. All on-site activities, workshops, and meetings conducted under this Purchase Order shall take place in Indonesia Jakarta unless otherwise agreed in writing. Travel and accommodation expenses for the Curriculum Developer team exceeding 50 km from Jakarta Central shall be borne by the Buyer at actual cost, capped at IDR 5,000,000 per person per day.
1. The Curriculum Developer shall maintain full compliance with all applicable Indonesian labor laws, data protection regulations (UU PDP No. 27/2022), and educational standards when developing curriculum content for students in the Indonesia Jakarta region.
1. Confidentiality: Both parties agree to treat all proprietary information exchanged under this Purchase Order as strictly confidential. The Curriculum Developer shall not disclose the Buyer's internal educational strategies, student data, or institutional plans to any third party.
1. Termination: Either party may terminate this Purchase Order with 30 days' written notice. In the event of termination, the Curriculum Developer shall deliver all work-in-progress materials and the Buyer shall pay for completed and accepted work only.
1. Dispute Resolution: Any disputes arising from this Purchase Order shall first be resolved through amicable negotiation in Indonesia Jakarta. If unresolved within 30 days, the matter shall be submitted to the Commercial Court of Jakarta (Pengadilan Negeri Jakarta Pusat) for adjudication under Indonesian law.
1. Force Majeure: Neither party shall be liable for delays caused by natural disasters, government mandates, or public health emergencies affecting operations in Indonesia Jakarta, provided that written notice is given within 5 business days of the event.
7. Acceptance & Authorization
By signing below, both parties acknowledge and accept all terms, conditions, pricing, and deliverables specified in this Purchase Order for the engagement of the Curriculum Developer in the Indonesia Jakarta region. This document is valid for a period of 90 days from the date of issue, after which a new Purchase Order must be generated if the engagement has not commenced.
For the Buyer
Nusantara Educational Solutions PT
Name: ___________________________
Title: Director of Procurement
Date: ___________________________
For the Curriculum Developer
Arus Pendidikan Kreatif CV
Name: ___________________________
Title: Managing Director
Date: ___________________________
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