# Purchase Order - Electrical Engineer Services - China Guangzhou

# PURCHASE ORDER

Professional Services Procurement Document

Reference: PO-CGZ-2025-00472

Date of Issue: 15 June 2025
Purchase Order No.: PO-CGZ-2025-00472
Validity Period: 90 days from issue date

Project Location: China Guangzhou
Site Address: 88 Tianhe Road, Tianhe District,
Guangzhou, Guangdong Province, China 510620
Project Code: CGZ-EE-2025-019

1. Parties to This Purchase Order

| Buyer (Procuring Entity) | Supplier (Service Provider) |
| --- | --- |
| Guangzhou Metro Development Corporation Ltd. 88 Tianhe Road, Tianhe District Guangzhou, Guangdong Province, China 510620 Tax ID: 91440101MA5C8X2K7P Contact: procurement@gzmetro.cn Tel: +86-20-8765-4321 | Shenzhen PowerGrid Engineering Consultants Co., Ltd. 120 Keji South Road, Nanshan District Shenzhen, Guangdong Province, China 518057 Tax ID: 91440300MA5D3R9T2L Contact: contracts@szpowergrid.cn Tel: +86-755-2345-6789 |

2. Scope of Services – Electrical Engineer Engagement

This Purchase Order is issued by Guangzhou Metro Development Corporation Ltd. (hereinafter referred to as the "Buyer") to procure the professional services of a qualified Electrical Engineer (hereinafter referred to as the "Service Provider") for the design, review, and commissioning of high-voltage electrical infrastructure associated with the Guangzhou Metro Line 18 Extension Project. The Electrical Engineer shall be physically stationed at the project site located in China Guangzhou for the entire duration of the engagement as specified in this Purchase Order.

The Electrical Engineer engaged under this Purchase Order shall hold a valid PRC Registered Electrical Engineer (Registered Electrical Engineer) license issued by the Ministry of Housing and Urban-Rural Development of the People's Republic of China, with a minimum of ten (10) years of documented experience in high-voltage power distribution systems, substation design, and metro rail electrical infrastructure. The Electrical Engineer must be proficient in both Mandarin Chinese and English to facilitate all technical documentation, site inspections, and regulatory submissions within China Guangzhou.

3. Detailed Service Description and Deliverables

| No. | Description of Service | Duration | Location | Amount (CNY) |
| --- | --- | --- | --- | --- |
| 1 | Site survey and load assessment for 110kV substation design at Guangzhou Metro Line 18 Extension, Phase II. The Electrical Engineer shall conduct comprehensive on-site measurements and produce a detailed load flow analysis report. | 30 days | China Guangzhou, Tianhe District | ¥ 185,000.00 |
| 2 | Preparation of complete single-line diagrams, protection relay coordination studies, and cable sizing calculations for the 35kV and 10kV distribution networks. All deliverables must comply with GB 50052-2009 and local China Guangzhou municipal electrical codes. | 45 days | China Guangzhou, Tianhe District | ¥ 320,000.00 |
| 3 | Commissioning and testing supervision of all electrical equipment including transformers, switchgear, SCADA systems, and emergency power supply units. The Electrical Engineer shall be present on-site for all hot-energization procedures. | 60 days | China Guangzhou, Tianhe District | ¥ 410,000.00 |
| 4 | Regulatory compliance review and submission of all electrical design documentation to the Guangzhou Municipal Housing and Urban-Rural Development Bureau and the Guangdong Provincial Electric Power Regulatory Office for final approval. | 30 days | China Guangzhou, Yuexiu District | ¥ 95,000.00 |
| 5 | Preparation of as-built documentation, operation and maintenance manuals, and a 12-month post-commissioning warranty support period during which the Electrical Engineer shall respond to any electrical anomalies within 24 hours. | 12 months | China Guangzhou (remote + on-site) | ¥ 250,000.00 |

4. Total Purchase Order Value

| Subtotal (CNY) | ¥ 1,260,000.00 |
| --- | --- |
| VAT (13% – applicable to professional engineering services in China) | ¥ 163,800.00 |
| Total Purchase Order Value (CNY) | ¥ 1,423,800.00 |
| Total in Words: | One Million Four Hundred Twenty-Three Thousand Eight Hundred Yuan Only |

5. Payment Terms

Payment under this Purchase Order shall be made in Renminbi (CNY) via bank transfer to the Service Provider's designated account. The payment schedule is as follows:

- Advance Payment (20%): ¥ 284,760.00 – payable within fifteen (15) business days of mutual execution of this Purchase Order and receipt of a valid VAT invoice (fapiao) from the Service Provider.

- Progress Payment (40%): ¥ 569,520.00 – payable upon completion and Buyer's written acceptance of Deliverables 1 and 2 as outlined in Section 3 of this Purchase Order.

- Completion Payment (30%): ¥ 427,140.00 – payable upon successful commissioning, regulatory approval, and handover of all as-built documentation for the Electrical Engineer's scope of work in China Guangzhou.

- Warranty Retention (10%): ¥ 142,380.00 – payable twelve (12) months after the completion date, subject to satisfactory performance of the warranty support obligations.

6. Terms and Conditions

- This Purchase Order shall be governed by and construed in accordance with the Civil Code of the People's Republic of China and all applicable electrical engineering regulations in force in China Guangzhou.

- The Electrical Engineer shall maintain valid professional liability insurance with a minimum coverage of ¥ 5,000,000.00 for the entire duration of the engagement. A certificate of insurance shall be provided to the Buyer prior to commencing any on-site work in China Guangzhou.

- All work performed under this Purchase Order shall comply with the National Electrical Engineering Standards of China (GB series), the Guangdong Provincial Electrical Safety Regulations, and the Guangzhou Municipal Construction Quality Supervision requirements.

- The Service Provider shall not subcontract any portion of the Electrical Engineer services without prior written consent from the Buyer. Any approved subcontracting shall not relieve the Service Provider of its obligations under this Purchase Order.

- Confidentiality: All technical drawings, load data, and project information pertaining to the Guangzhou Metro Line 18 Extension shall be treated as strictly confidential. The Electrical Engineer shall not disclose any project-specific information to third parties without the Buyer's written authorization.

- Dispute Resolution: Any dispute arising from or in connection with this Purchase Order shall first be resolved through amicable negotiation. If unresolved within thirty (30) days, the dispute shall be submitted to the Guangzhou Arbitration Commission for arbitration in China Guangzhou. The arbitration award shall be final and binding.

- Force Majeure: Neither party shall be liable for delays or failures in performance caused by events beyond reasonable control, including but not limited to natural disasters, government-mandated shutdowns in China Guangzhou, or epidemics, provided that the affected party notifies the other in writing within five (5) business days.

- This Purchase Order becomes effective upon signature by both parties and remains valid until full completion of all deliverables and expiration of the warranty period.

7. Acceptance and Authorization

By signing below, both parties acknowledge that they have read, understood, and agree to all terms, conditions, and specifications set forth in this Purchase Order for the engagement of an Electrical Engineer for the Guangzhou Metro Line 18 Extension Project in China Guangzhou.

For and on behalf of the Buyer:

Guangzhou Metro Development Corporation Ltd.

Authorized Signatory
Name: _________________________
Title: Director of Procurement
Date: _________________________
Company Seal:

For and on behalf of the Supplier:

Shenzhen PowerGrid Engineering Consultants Co., Ltd.

Authorized Signatory
Name: _________________________
Title: Chief Electrical Engineer / Managing Director
Date: _________________________
Company Seal:

This Purchase Order (PO-CGZ-2025-00472) is a controlled document. Unauthorized reproduction or distribution is prohibited.
Issued by: Guangzhou Metro Development Corporation Ltd. – Procurement & Contracts Department, China Guangzhou.
Document Version: 1.0 | Classification: Commercial in Confidence