# Purchase Order - Environmental Engineer Services - Kazakhstan Almaty

# PURCHASE ORDER

Professional Services Procurement Document

Issued for Environmental Engineer Engagement in Kazakhstan Almaty

PO No. KZ-ALM-2025-00472

## 1. Purchase Order Details

| Purchase Order Number: | KZ-ALM-2025-00472 |
| --- | --- |
| Date of Issue: | 15 June 2025 |
| Required Delivery/Start Date: | 01 July 2025 |
| Project Location: | Kazakhstan Almaty, 050040, Almaty City, Republic of Kazakhstan |
| Payment Terms: | Net 30 days from invoice date |
| Currency: | USD (United States Dollars) |
| Valid Until: | 30 June 2025 |

## 2. Parties Involved

### Purchasing Party (Buyer)

Company: Almaty Green Infrastructure Development JSC

Address: 45 Abai Avenue, Almaty, 050040, Kazakhstan

BIN (Tax ID): 990440012345

Contact: Mr. Tolkyn Nurlanov, Procurement Director

Email: procurement@agid.kz

Phone: +7 (727) 312-45-67

### Supplier / Service Provider

Company: EcoConsult Central Asia LLP

Address: 12 Dostyk Avenue, Almaty, 050010, Kazakhstan

BIN (Tax ID): 990740067890

Contact: Dr. Aigerim Serikova, Managing Director

Email: info@ecoconsult-ca.com

Phone: +7 (727) 245-89-01

## 3. Scope of Work – Environmental Engineer Services

This Purchase Order is issued to formally engage a qualified Environmental Engineer to provide comprehensive environmental assessment, monitoring, and compliance services for the Almaty Metropolitan Green Corridor Project. The Environmental Engineer shall be based in Kazakhstan Almaty and shall report directly to the Project Environmental Management Office located at the Almaty Green Infrastructure Development JSC headquarters. The scope of work encompasses the following deliverables:

| Item No. | Description of Service | Quantity | Unit | Unit Price (USD) | Total (USD) |
| --- | --- | --- | --- | --- | --- |
| 001 | Environmental Impact Assessment (EIA) preparation for the Almaty Green Corridor Phase II, including baseline environmental data collection in Kazakhstan Almaty | 1 | Project | 48,500.00 | 48,500.00 |
| 002 | Air quality monitoring and dispersion modeling for industrial zones surrounding the project site in Kazakhstan Almaty | 12 | Months | 3,200.00 | 38,400.00 |
| 003 | Water resource assessment and hydrological survey of the Ili River tributaries within the Almaty municipal boundary | 1 | Project | 27,800.00 | 27,800.00 |
| 004 | Soil contamination testing and remediation strategy development for 14 identified sites in Kazakhstan Almaty | 14 | Sites | 4,150.00 | 58,100.00 |
| 005 | Waste management plan development and compliance audit per Kazakhstani environmental legislation (Law of the Republic of Kazakhstan No. 391-V "On Environmental Protection") | 1 | Project | 19,600.00 | 19,600.00 |
| 006 | Monthly environmental compliance reporting and stakeholder engagement sessions in Kazakhstan Almaty | 12 | Months | 1,850.00 | 22,200.00 |
| 007 | Final Environmental Engineer technical report, peer review, and submission to the Almaty City Committee for Ecology and Environmental Protection | 1 | Report | 12,400.00 | 12,400.00 |
| TOTAL PURCHASE ORDER VALUE: |  |  |  |  | 227,000.00 |

## 4. Qualification Requirements for the Environmental Engineer

The Environmental Engineer engaged under this Purchase Order must meet the following minimum qualifications:

- A minimum of a Master's degree in Environmental Engineering, Environmental Science, or a closely related discipline from an accredited university.

- A minimum of eight (8) years of progressive professional experience in environmental consulting, with at least three (3) years of experience conducting projects in Kazakhstan or Central Asian jurisdictions.

- Valid professional licensure or registration as an Environmental Engineer recognized by the relevant Kazakhstani regulatory authority.

- Demonstrated proficiency in environmental impact assessment methodologies compliant with the Law of the Republic of Kazakhstan on Environmental Protection and the Almaty City Environmental Code.

- Working knowledge of the Kazakh language is strongly preferred; English proficiency is mandatory for all technical documentation and reporting.

- Proven experience with air quality modeling software (AERMOD, CALPUFF), GIS platforms (ArcGIS, QGIS), and hydrological modeling tools.

## 5. Terms and Conditions

- 5.1 This Purchase Order constitutes a binding agreement between the Purchasing Party and the Supplier upon signature by both parties. All services described herein shall be performed in Kazakhstan Almaty unless otherwise specified in writing.

- 5.2 The Environmental Engineer shall adhere to all applicable environmental laws, regulations, and standards of the Republic of Kazakhstan, including but not limited to the Code of the Republic of Kazakhstan on Subsoil, the Law on Environmental Protection, and municipal regulations of Almaty City.

- 5.3 Payment shall be made in USD via bank transfer to the Supplier's designated account within thirty (30) calendar days of receipt of a valid invoice. Late payments shall accrue interest at a rate of 1.5% per month.

- 5.4 The Supplier shall provide a detailed project schedule within ten (10) business days of the Purchase Order acceptance date. All milestones shall be subject to approval by the Purchasing Party's Project Environmental Management Office in Kazakhstan Almaty.

- 5.5 The Environmental Engineer shall maintain professional liability insurance with a minimum coverage of USD 500,000 for the duration of the contract. Certificates of insurance shall be provided prior to the commencement of work.

- 5.6 All data, reports, and deliverables produced under this Purchase Order shall be the exclusive property of the Purchasing Party. The Supplier shall not disclose any project information to third parties without prior written consent.

- 5.7 Either party may terminate this Purchase Order with thirty (30) days' written notice. In the event of termination, the Supplier shall be compensated for all work completed and documented up to the termination date.

- 5.8 Disputes arising from this Purchase Order shall be resolved through arbitration in Almaty, Kazakhstan, in accordance with the rules of the Arbitration Center of the Astana International Financial Centre.

- 5.9 The Supplier shall ensure that the assigned Environmental Engineer is available on-site in Kazakhstan Almaty for a minimum of four (4) days per week during active project phases.

- 5.10 Force majeure events, including but not limited to natural disasters, government-imposed restrictions, or pandemics affecting operations in Kazakhstan Almaty, shall relieve the affected party from performance obligations for the duration of the event, provided written notice is given within five (5) business days.

## 6. Acceptance and Authorization

By signing below, both parties acknowledge and agree to all terms, conditions, and specifications outlined in this Purchase Order for the engagement of an Environmental Engineer in Kazakhstan Almaty. This document is executed in two (2) original copies, one for each party.

For the Purchasing Party:

Almaty Green Infrastructure Development JSC

Name: Tolkyn Nurlanov

Title: Procurement Director

Signature: _________________________

Date: _________________________

For the Supplier:

EcoConsult Central Asia LLP

Name: Dr. Aigerim Serikova

Title: Managing Director

Signature: _________________________

Date: _________________________

Purchase Order No. KZ-ALM-2025-00472 | Environmental Engineer Services | Kazakhstan Almaty

Almaty Green Infrastructure Development JSC | 45 Abai Avenue, Almaty, 050040, Republic of Kazakhstan

This Purchase Order is valid only when signed and stamped by both parties. Unauthorized reproduction is prohibited.