# Purchase Order - Mason Services - Pakistan Karachi

# PURCHASE ORDER

Al-Madina Construction & Development (Pvt.) Ltd.

Plot 47-B, Clifton Block 5, Karachi, Sindh, Pakistan

Phone: +92-21-3587-4421 | Email: procurement@almadinakhi.com | NTN: 7821456-3

PO No: AMCD-2025-0847
Date of Issue: 14 June 2025
Valid Until: 14 July 2025

### Issued By (Buyer)

Company: Al-Madina Construction & Development (Pvt.) Ltd.

Address: Plot 47-B, Clifton Block 5, Karachi, Sindh, Pakistan

Contact Person: Mr. Ahmed Raza, Procurement Manager

Phone: +92-300-4567890

Email: a.raza@almadinakhi.com

### Issued To (Mason Contractor / Vendor)

Company: Karachi Mason & Tile Works (Pvt.) Ltd.

Address: Shop 12, Saddar Bazaar, Karachi, Sindh, Pakistan

Contact Person: Mr. Muhammad Iqbal, Chief Mason & Site Supervisor

Phone: +92-321-7894563

Email: info@karachimasonworks.pk

NTN: 6543210-8

Project Details – Pakistan Karachi

This Purchase Order is issued for the procurement of professional Mason services, masonry materials, and related construction labour for the residential and commercial building project located at Pakistan Karachi, specifically at the Al-Madina Heights development site in DHA Phase 6, Karachi. The Mason contractor shall be responsible for all brickwork, block masonry, plastering, tiling, and finishing works as per the approved architectural and structural drawings. All work shall comply with the Pakistan Building Code (PBC) 2018 and the local by-laws enforced by the Karachi Metropolitan Corporation (KMC) and the Sindh Building Authority.

Scope of Work – Mason Services

| S.No | Description of Mason Work / Item | Unit | Quantity | Unit Rate (PKR) | Total Amount (PKR) | Timeline |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Brick masonry work (13.5" thick external walls) – 1st to 4th floor, including mortar mixing, laying, and curing | SQM | 1,250 | 3,850 | 4,812,500 | Weeks 1–6 |
| 2 | Internal partition wall masonry (9" thick) using solid clay bricks | SQM | 820 | 3,200 | 2,624,000 | Weeks 4–9 |
| 3 | Internal and external plastering (12mm thick, cement-sand 1:4 mix) – all floors | SQM | 4,600 | 1,450 | 6,670,000 | Weeks 8–14 |
| 4 | Ceramic tile laying (bathroom, kitchen, and utility areas) – 600mm x 600mm tiles | SQM | 1,100 | 2,800 | 3,080,000 | Weeks 12–16 |
| 5 | Stone cladding and granite finishing for ground floor lobby and entrance façade | SQM | 340 | 5,500 | 1,870,000 | Weeks 14–18 |
| 6 | Mason labour for staircase construction, balustrade masonry, and decorative brickwork | LSM | 180 | 4,200 | 756,000 | Weeks 6–12 |
| 7 | Supply and application of waterproofing membrane on terrace and bathroom slabs (Mason-applied) | SQM | 650 | 1,900 | 1,235,000 | Weeks 10–13 |
| 8 | Site supervision by senior Mason foreman, quality inspection, and daily progress reporting | Month | 5 | 185,000 | 925,000 | Weeks 1–20 |
| SUBTOTAL |  |  |  |  | 21,972,500 |  |
| Sales Tax (18% as per FBR Pakistan) |  |  |  |  | 3,955,050 |  |
| GRAND TOTAL (PKR) |  |  |  |  | 25,927,550 |  |

Terms and Conditions

- This Purchase Order constitutes a binding agreement between Al-Madina Construction & Development (Pvt.) Ltd. and Karachi Mason & Tile Works (Pvt.) Ltd. for the execution of all Mason works at the designated site in Pakistan Karachi.

- The Mason contractor shall mobilize all skilled masons, helpers, tools, and equipment to the Karachi site within three (3) working days of the acceptance of this Purchase Order.

- Payment shall be made in monthly progress installments based on certified work completion. A 10% retention shall be withheld from each installment and released upon final handover and defect-liability period expiry (twelve months).

- All masonry materials (bricks, cement, sand, tiles, granite, waterproofing compounds) shall be sourced from approved suppliers in Karachi and shall meet the Pakistan Standards & Quality Control Authority (PSQCA) specifications.

- The Mason contractor is responsible for the safety of all workers on site in compliance with the Occupational Health and Safety (OHS) regulations of the Sindh Labour Department, Karachi.

- Any variation or change order to the scope of Mason work must be approved in writing by the Buyer's Project Engineer before execution. No additional payment shall be made for unapproved variations.

- The Mason contractor shall submit a detailed weekly progress report every Friday to the Buyer's site office in Karachi, including photographs, quantity measurements, and material consumption logs.

- In the event of force majeure (including but not limited to monsoon flooding common in Karachi, government-imposed work stoppages, or natural disasters), the affected party shall notify the other within 48 hours, and the project timeline shall be extended equitably.

- All disputes arising from this Purchase Order shall be resolved through arbitration in Karachi, Sindh, Pakistan, in accordance with the Arbitration Act, 1940 of Pakistan. The language of arbitration shall be English.

- This Purchase Order is governed by the laws of the Islamic Republic of Pakistan. The jurisdiction of the courts of Karachi, Sindh, shall be exclusive.

- The Mason contractor shall maintain valid insurance coverage (workmen's compensation and third-party liability) for the entire duration of the project in Pakistan Karachi.

Payment Schedule

| Milestone | Percentage | Amount (PKR) | Due Date |
| --- | --- | --- | --- |
| Advance (upon PO acceptance) | 15% | 3,889,133 | Within 7 days of acceptance |
| Monthly progress (Weeks 1–19) | 70% | 18,149,285 | Monthly, within 14 days of certification |
| Final handover (after defect-free inspection) | 10% | 2,592,755 | Upon final acceptance |
| Retention release | 5% | 1,296,377 | 12 months after handover |

For and on behalf of the Buyer:

Al-Madina Construction & Development (Pvt.) Ltd.

Mr. Ahmed Raza
Procurement Manager
Signature & Company Seal

For and on behalf of the Mason Contractor:

Karachi Mason & Tile Works (Pvt.) Ltd.

Mr. Muhammad Iqbal
Chief Mason & Site Supervisor
Signature & Company Seal

This Purchase Order (AMCD-2025-0847) is issued for Mason services at the Al-Madina Heights project, DHA Phase 6, Karachi, Sindh, Pakistan.

Document generated on 14 June 2025 | Page 1 of 1 | Confidential – For Authorized Use Only

Al-Madina Construction & Development (Pvt.) Ltd. | Karachi, Pakistan | NTN: 7821456-3