Purchase Order - Telecommunication Engineer Services - Nigeria Lagos
PURCHASE ORDER
Telecommunication Engineer Services Procurement
Project Location: Nigeria Lagos
Document Reference: PO-TEL-2025-0047
Purchase Order No.: PO-TEL-2025-0047
Date of Issue: 14 June 2025
Valid Until: 14 September 2025
Buyer: Lagos Infrastructure Development Authority (LIDA)
Address: 12 Adeola Odeku Street, Victoria Island, Nigeria Lagos
Contact: procurement@lida.ng | +234-801-234-5678
Supplier / Contractor: NexaTel Engineering Solutions Ltd.
Address: 45 Marina Road, Apapa, Nigeria Lagos
Contact: contracts@nexatel.ng | +234-802-345-6789
1. Scope of Purchase Order
This Purchase Order is issued by the Lagos Infrastructure Development Authority (hereinafter referred to as the "Buyer") to NexaTel Engineering Solutions Ltd. (hereinafter referred to as the "Supplier") for the engagement of a qualified Telecommunication Engineer to provide comprehensive design, installation, testing, and commissioning services for the fibre-optic backbone network and associated wireless infrastructure across the Nigeria Lagos metropolitan area. This Purchase Order governs all terms, conditions, deliverables, and financial obligations related to the procurement of the aforementioned Telecommunication Engineer services.
2. Line Items and Service Description
	Item No.
	Description of Service
	Quantity
	Unit
	Unit Price (NGN)
	Total (NGN)

	01
	Engagement of a senior Telecommunication Engineer (minimum 10 years' experience) for network architecture design of the Nigeria Lagos fibre-optic backbone spanning 340 km of cable routes.
	1
	Professional
	4,500,000
	4,500,000

	02
	On-site supervision by the Telecommunication Engineer for the physical installation of underground and aerial fibre-optic cables across 12 districts in Nigeria Lagos, including Lekki, Ikeja, Surulere, and Yaba.
	180
	Working Days
	85,000
	15,300,000

	03
	Design and deployment of 4G/5G base station sites (minimum 45 towers) by the Telecommunication Engineer, including RF planning, antenna alignment, and backhaul configuration in Nigeria Lagos.
	45
	Sites
	1,200,000
	54,000,000

	04
	Testing, commissioning, and performance validation of all Telecommunication Engineer-installed infrastructure, including OTDR testing, BER analysis, and throughput verification across the Nigeria Lagos network.
	1
	Lump Sum
	7,800,000
	7,800,000

	05
	Preparation of as-built documentation, network topology diagrams, and operational handover manuals by the Telecommunication Engineer for the Nigeria Lagos project.
	1
	Lump Sum
	2,400,000
	2,400,000

	06
	Post-commissioning support and warranty period (12 months) provided by the Telecommunication Engineer for fault diagnosis, corrective maintenance, and performance monitoring in Nigeria Lagos.
	12
	Months
	350,000
	4,200,000

	TOTAL CONTRACT VALUE (NGN):
	88,200,000


3. Payment Terms
All payments under this Purchase Order shall be made in Nigerian Naira (NGN) via bank transfer to the Supplier's designated account. The payment schedule for the Telecommunication Engineer services is structured as follows:
· 20% Advance Payment (NGN 17,640,000): Payable within 14 calendar days of the Buyer's written acceptance of this Purchase Order and receipt of a valid Performance Bond from the Supplier.
· 30% Milestone Payment (NGN 26,460,000): Payable upon completion and Buyer's sign-off of the fibre-optic cable installation phase (Item 02) across all 12 districts in Nigeria Lagos.
· 30% Milestone Payment (NGN 26,460,000): Payable upon successful commissioning and testing of all 45 base station sites (Item 03) as verified by the Telecommunication Engineer's test reports.
· 20% Final Payment (NGN 17,640,000): Payable upon full project handover, submission of all as-built documentation, and commencement of the 12-month warranty period.
4. Delivery and Commencement
The Telecommunication Engineer shall commence all activities under this Purchase Order no later than 1 July 2025 at the designated project sites within Nigeria Lagos. The overall project duration shall not exceed 270 calendar days from the commencement date. All work shall be conducted in strict compliance with the Nigerian Communications Commission (NCC) regulations, the Lagos State Building Control and Road Authority (LASBCRA) guidelines, and applicable international telecommunication engineering standards (ITU-T, ETSI).
5. Terms and Conditions
· The Telecommunication Engineer engaged under this Purchase Order must hold a valid professional registration with the Council for the Regulation of Engineering in Nigeria (COREN) and possess a minimum of ten (10) years of documented experience in fibre-optic and wireless telecommunication infrastructure projects.
· The Supplier shall provide a Performance Bond equivalent to 10% of the total Purchase Order value, issued by a Tier-1 Nigerian bank, prior to the release of the advance payment.
· All work performed by the Telecommunication Engineer in Nigeria Lagos shall be subject to inspection and approval by the Buyer's appointed project manager. No milestone payment shall be released without a written Certificate of Completion signed by both parties.
· The Supplier shall maintain comprehensive third-party liability insurance and professional indemnity insurance throughout the duration of this Purchase Order, with minimum coverage of NGN 500,000,000.
· Any variation to the scope of work described in this Purchase Order must be agreed upon in writing by both parties before execution. Verbal instructions shall not constitute a valid amendment to this Purchase Order.
· In the event of a dispute arising from this Purchase Order, both parties shall first attempt resolution through mediation in Nigeria Lagos. Should mediation fail, the matter shall be referred to arbitration under the rules of the Lagos Court of Arbitration.
· The Supplier shall comply with all applicable Nigerian labour laws, including the minimum wage provisions of the Lagos State Government, for all personnel deployed under this Purchase Order.
· Confidentiality: All network design documents, security protocols, and operational data generated by the Telecommunication Engineer in the course of this Purchase Order shall be treated as strictly confidential and shall not be disclosed to any third party without the Buyer's prior written consent.
IMPORTANT NOTE: This Purchase Order is subject to the Buyer's internal budget approval and the successful completion of the Supplier's due diligence verification. The Buyer reserves the right to cancel or modify this Purchase Order in whole or in part with 30 days' written notice, in which case the Supplier shall be compensated for all work completed and materials procured up to the date of cancellation.
6. Acceptance and Authorization
By signing below, both parties acknowledge and agree to all terms, conditions, and obligations set forth in this Purchase Order for the procurement of Telecommunication Engineer services in Nigeria Lagos.
For and on behalf of the Buyer
Lagos Infrastructure Development Authority
Name: ___________________________
Title: Director of Procurement
Date: ___________________________
For and on behalf of the Supplier
NexaTel Engineering Solutions Ltd.
Name: ___________________________
Title: Managing Director
Date: ___________________________
This Purchase Order (PO-TEL-2025-0047) is a legally binding document governing the procurement of Telecommunication Engineer services for the Nigeria Lagos metropolitan infrastructure project. Issued by Lagos Infrastructure Development Authority, Victoria Island, Nigeria Lagos. © 2025 LIDA. All rights reserved.
