# Purchase Order - Videographer Services - Pakistan Karachi

# PURCHASE ORDER

Videographer Services — Pakistan Karachi

Purchase Order No.: PO-KHI-2025-04782
Date of Issue: 14 June 2025
Valid Until: 14 July 2025

Project Reference: VDG-KHI-2025-Q2
Priority: High
Payment Terms: Net 30 Days

## 1. Buyer Information

| Field | Details |
| --- | --- |
| Company Name | Al-Noor Media & Communications (Pvt.) Ltd. |
| Address | Suite 412, Ocean Mall, Clifton Block 5, Pakistan Karachi, Sindh 75600 |
| Contact Person | Ms. Ayesha Raza, Procurement Manager |
| Email | procurement@alnoormedia.pk |
| Phone | +92-21-3587-4421 |
| NTN / Tax No. | 7821456-3 |

## 2. Vendor / Supplier Information (Videographer)

| Field | Details |
| --- | --- |
| Vendor Name | FrameCraft Visuals — Professional Videographer Services |
| Address | Plot 88, Shahrah-e-Faisal, DHA Phase 6, Pakistan Karachi, Sindh 75500 |
| Contact Person | Mr. Hamza Qureshi, Lead Videographer & Director |
| Email | hamza@framecraftvisuals.pk |
| Phone | +92-300-845-6721 |
| NTN / Tax No. | 6934782-1 |
| Bank Details | HBL, Account No. 0045-8821-3367-9912, IFSC: HBLAPAK |

## 3. Scope of Work & Line Items

This Purchase Order is issued to engage a professional Videographer and associated production crew for the filming, editing, and post-production of a corporate brand campaign to be executed in Pakistan Karachi. The Videographer shall be responsible for all aspects of on-site video capture, including but not limited to camera operation, lighting setup, audio recording, and preliminary editing. All production activities shall take place at locations within the metropolitan area of Pakistan Karachi, including Clifton, Gulshan-e-Iqbal, and the Karachi Port Trust industrial zone.

| Item # | Description of Service | Qty | Unit | Unit Price (PKR) | Total (PKR) |
| --- | --- | --- | --- | --- | --- |
| 1 | Lead Videographer & Director — On-site filming (3 full days in Pakistan Karachi) | 3 | Days | 185,000 | 555,000 |
| 2 | Assistant Videographer / Camera Operator (2 additional cameras) | 3 | Days | 75,000 | 225,000 |
| 3 | Professional Lighting & Audio Equipment Rental (LED panels, boom mics, wireless lavs) | 3 | Days | 45,000 | 135,000 |
| 4 | Drone Videography — Aerial footage of Karachi coastline and industrial sites | 1 | Day | 120,000 | 120,000 |
| 5 | Post-Production: Editing, Color Grading, Sound Mixing & Final Delivery (4K) | 1 | Project | 350,000 | 350,000 |
| 6 | Travel & Local Transportation within Pakistan Karachi (all production days) | 3 | Days | 12,000 | 36,000 |
| 7 | Location Permits & Coordination (Karachi Port Trust, Clifton Beach access) | 1 | Lot | 65,000 | 65,000 |
| Subtotal |  |  |  |  | 1,486,000 |
| Sales Tax (18% — Sindh Province, Pakistan) |  |  |  |  | 267,480 |
| Grand Total (PKR) |  |  |  |  | 1,753,480 |

## 4. Production Schedule & Delivery Milestones

| Milestone | Target Date | Location (Pakistan Karachi) |
| --- | --- | --- |
| Pre-Production Meeting & Storyboard Approval | 20 June 2025 | Al-Noor Media Office, Clifton |
| Principal Filming — Day 1 (Corporate Office & Staff Interviews) | 23 June 2025 | Gulshan-e-Iqbal, Pakistan Karachi |
| Principal Filming — Day 2 (Industrial & Port Footage) | 24 June 2025 | Karachi Port Trust, Pakistan Karachi |
| Principal Filming — Day 3 (Drone & B-Roll, Clifton Beach) | 25 June 2025 | Clifton Beach, Pakistan Karachi |
| Rough Cut Delivery for Client Review | 05 July 2025 | Digital Delivery |
| Final Edit, Color Grade & Master Delivery (4K ProRes + H.264) | 15 July 2025 | Digital Delivery |

## 5. Terms & Conditions

- This Purchase Order constitutes a binding agreement between Al-Noor Media & Communications (Pvt.) Ltd. and FrameCraft Visuals upon written acceptance by both parties. The Videographer shall commence work only after receiving a signed copy of this Purchase Order.

- All services described herein shall be performed by the Videographer and their designated crew at the specified locations within Pakistan Karachi. The Videographer is responsible for obtaining all necessary local permits, insurance, and safety clearances required by the Sindh Provincial Government and relevant municipal authorities in Pakistan Karachi.

- Payment shall be made in two installments: 40% (PKR 701,392) upon signing of this Purchase Order, and 60% (PKR 1,052,088) within thirty (30) calendar days of final delivery and written acceptance of the completed video assets.

- The Videographer warrants that all footage, edits, and deliverables shall be original work free from any third-party intellectual property claims. All music, stock footage, and licensed assets used in the final production shall be fully cleared and documented.

- Full ownership and all intellectual property rights to the final video deliverables shall transfer to Al-Noor Media upon full payment. The Videographer retains the right to include the project in their professional portfolio, subject to a 90-day embargo period from the date of final delivery.

- In the event of weather-related delays (monsoon conditions common in Pakistan Karachi during June–July), the Videographer shall notify the Buyer within four (4) hours, and the production schedule shall be adjusted by mutual written agreement without additional cost to either party.

- The Videographer shall maintain comprehensive public liability insurance with a minimum coverage of PKR 10,000,000 for all personnel and equipment operating in Pakistan Karachi during the production period.

- Any changes to scope, additional filming days, or revised deliverable specifications must be documented in a written Change Order signed by both parties before execution. Unauthorized scope changes shall not be compensated under this Purchase Order.

- This Purchase Order shall be governed by and construed in accordance with the laws of the Islamic Republic of Pakistan. Any disputes arising from this Purchase Order shall be resolved through arbitration in Pakistan Karachi in accordance with the Arbitration Act, 1940.

- The Videographer shall comply with all applicable data protection and privacy regulations when filming individuals in Pakistan Karachi, including obtaining written consent from all identifiable persons appearing in the footage.

## 6. Acceptance & Authorization

By signing below, both parties acknowledge and agree to all terms, conditions, and specifications outlined in this Purchase Order for the engagement of the Videographer for the production of the corporate brand campaign in Pakistan Karachi.

For and on behalf of the Buyer
Al-Noor Media & Communications (Pvt.) Ltd.

Name: Ayesha Raza
Title: Procurement Manager
Date: _______________

For and on behalf of the Videographer / Vendor
FrameCraft Visuals

Name: Hamza Qureshi
Title: Lead Videographer & Director
Date: _______________

[ COMPANY STAMP / SEAL ]

Purchase Order No. PO-KHI-2025-04782 — Videographer Services — Pakistan Karachi
This document is the property of Al-Noor Media & Communications (Pvt.) Ltd. Unauthorized reproduction or distribution is prohibited.
Generated on 14 June 2025 | Page 1 of 1