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Professional Academic Researcher Services — Egypt Cairo
Nile Delta Research & Consultancy Group
	Quotation Estimate No.
	QTE-EGY-CAI-2025-0472

	Date of Issue
	14 June 2025

	Valid Until
	14 July 2025 (30 calendar days)

	Prepared For (Client)
	Faculty of Social Sciences, Cairo University — 12611 Giza, Egypt Cairo

	Prepared By
	Nile Delta Research & Consultancy Group, 45 El Tahrir Square, Downtown, Egypt Cairo

	Contact Person
	Dr. Amira Hassan, Director of Research Operations

	Currency
	Egyptian Pound (EGP) / US Dollar (USD)


1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is issued by Nile Delta Research & Consultancy Group to formally outline the costs, deliverables, and professional terms associated with the engagement of a qualified Academic Researcher to conduct a comprehensive mixed-methods study on urban development patterns in the Greater Cairo metropolitan area. The engagement is specifically tailored to the academic, regulatory, and logistical environment of Egypt Cairo, ensuring full compliance with local research ethics, data protection regulations, and institutional review board requirements.
The Academic Researcher proposed for this assignment holds a Ph.D. in Urban Planning from the American University in Cairo, possesses over twelve years of peer-reviewed publication experience, and has previously led three funded research projects in partnership with the Egyptian National Research Centre. The researcher will be based in Egypt Cairo for the full duration of the project to facilitate fieldwork, stakeholder interviews, and institutional coordination.
2. Itemized Cost Breakdown
	#
	Description of Service
	Duration
	Rate (EGP)
	Total (EGP)

	1
	Academic Researcher monthly professional fee (Ph.D. level, full-time dedication)
	6 months
	45,000 / month
	270,000

	2
	Literature review and systematic bibliographic analysis (Arabic and English sources)
	1 month
	35,000 (lump sum)
	35,000

	3
	Fieldwork coordination and data collection in 12 districts of Egypt Cairo
	3 months
	28,000 / month
	84,000

	4
	Stakeholder interviews with municipal officials, NGOs, and community leaders in Cairo
	2 months
	22,000 / month
	44,000

	5
	Quantitative and qualitative data analysis using SPSS and NVivo software
	2 months
	30,000 / month
	60,000

	6
	Drafting of research report, journal articles, and policy brief for submission
	2 months
	32,000 / month
	64,000

	7
	Travel, accommodation, and local transportation within Egypt Cairo
	6 months
	12,000 / month
	72,000

	8
	Research ethics committee submission and institutional review fees (Cairo University IRB)
	One-time
	8,500 (lump sum)
	8,500

	9
	Translation of final deliverables (Arabic to English and vice versa)
	1 month
	15,000 (lump sum)
	15,000

	10
	Project management, reporting, and administrative oversight
	6 months
	10,000 / month
	60,000

	SUBTOTAL
	708,500

	VAT (14% — Egyptian Tax Authority)
	99,190

	GRAND TOTAL
	807,690 EGP

	GRAND TOTAL (USD equivalent at EGP 48.50/USD)
	16,653 USD


3. Deliverables and Milestones
The Academic Researcher shall deliver the following outputs at defined intervals, all of which are subject to the client's review and written approval before the next phase commences:
1. Month 1: Approved research proposal, detailed methodology document, and ethics clearance from the Cairo University Institutional Review Board.
1. Month 3: Interim progress report with preliminary fieldwork findings from at least six districts of Egypt Cairo.
1. Month 5: Complete dataset, coded interview transcripts, and statistical analysis summary.
1. Month 6: Final research report (minimum 120 pages), two peer-reviewed journal article manuscripts, and one policy brief formatted for submission to the Egyptian Ministry of Housing and Urban Development.
4. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any engagement initiated after the expiry date will require a revised quotation reflecting current market rates in Egypt Cairo.
1. Payment shall be made in three equal installments: 40% upon contract signing, 30% upon delivery of the interim report (Month 3), and 30% upon final acceptance of all deliverables.
1. All intellectual property rights in the final research outputs shall vest with the client. The Academic Researcher retains the right to cite the work in future academic publications with prior written consent.
1. The Academic Researcher shall comply with all applicable Egyptian laws, including the Personal Data Protection Law (Law No. 151 of 2020) and the regulations of the Egyptian National Research Authority.
1. Any scope changes exceeding 10% of the originally agreed workload will be subject to a supplementary Quotation Estimate issued within five (5) business days.
1. Force majeure events, including but not limited to civil unrest, government-mandated closures, or public health emergencies affecting Egypt Cairo, shall suspend the project timeline without penalty to either party.
1. Disputes arising from this engagement shall be resolved through arbitration in accordance with the rules of the Egyptian Arbitration Centre, with the seat of arbitration in Cairo, Egypt.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the engagement of the proposed Academic Researcher in Egypt Cairo.
For Nile Delta Research & Consultancy Group
Name: Dr. Amira Hassan
Title: Director of Research Operations
Signature: _________________________
Date: _________________________
For the Client (Cairo University)
Name: _________________________
Title: _________________________
Signature: _________________________
Date: _________________________
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