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1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is issued by our firm to provide a comprehensive and transparent breakdown of costs associated with the engagement of a qualified Academic Researcher for a structured research project commissioned by the Department of Social Sciences, Mumbai University. The scope of this engagement is specifically tailored to the academic, regulatory, and operational environment of India Mumbai, taking into account local institutional requirements, applicable tax regulations under the Government of India, and the specific research needs of the client. This document serves as a formal proposal and cost estimate, and upon acceptance, it shall form the basis of a binding service agreement between the parties.
2. Scope of Work – Academic Researcher Engagement
The Academic Researcher to be engaged under this Quotation Estimate shall perform the following duties and deliverables over a period of twelve (12) months, commencing from the date of contract execution:
	Sr. No.
	Activity / Deliverable
	Details
	Duration

	1
	Literature Review & Research Design
	Comprehensive review of existing literature on urban migration patterns in metropolitan India; formulation of a mixed-methods research design.
	Months 1–2

	2
	Field Data Collection – India Mumbai
	Primary data collection through structured surveys, in-depth interviews, and focus group discussions across 12 wards in Mumbai city, covering areas in Mumbai Suburban and Mumbai City districts.
	Months 3–6

	3
	Data Analysis & Interpretation
	Quantitative statistical analysis using SPSS and R; qualitative thematic coding of interview transcripts; triangulation of findings.
	Months 7–9

	4
	Report Writing & Manuscript Preparation
	Preparation of a 150-page research report, two peer-reviewed journal articles, and a policy brief suitable for submission to the Maharashtra State Government.
	Months 10–11

	5
	Conference Presentation & Dissemination
	Presentation of findings at the National Conference on Urban Studies, New Delhi, and a local seminar at Mumbai University, India Mumbai.
	Month 12


3. Itemized Cost Breakdown
	Sr. No.
	Description
	Unit
	Rate (INR)
	Quantity
	Amount (INR)

	1
	Academic Researcher – Professional Fee (PhD-qualified, 10+ years experience)
	Month
	1,85,000
	12
	22,20,000

	2
	Research Assistant (M.Phil level) – Support Staff
	Month
	65,000
	12
	7,80,000

	3
	Fieldwork Travel & Logistics within India Mumbai (local transport, accommodation for field teams)
	Lump Sum
	—
	1
	3,50,000

	4
	Survey Instruments, Printing & Stationery
	Lump Sum
	—
	1
	1,20,000

	5
	Software Licenses (SPSS, NVivo, R Studio) – Annual
	Lump Sum
	—
	1
	95,000

	6
	Transcription & Translation Services (Marathi, Hindi, English)
	Lump Sum
	—
	1
	1,80,000

	7
	Conference Registration, Travel & Accommodation (New Delhi)
	Lump Sum
	—
	1
	85,000

	8
	Publication Charges (2 journal articles + 1 policy brief)
	Lump Sum
	—
	1
	1,50,000

	9
	Administrative & Overhead Costs (office space, utilities, insurance)
	Lump Sum
	—
	1
	2,20,000

	10
	Applicable GST @ 18% (as per Indian tax regulations)
	—
	—
	—
	8,37,900

	Grand Total (INR)
	40,37,900


Grand Total in words: Rupees Forty Lakh Thirty-Seven Thousand Nine Hundred Only (₹40,37,900/-)
4. Payment Schedule
	Milestone
	Percentage
	Amount (INR)
	Due Date

	Advance (upon signing of agreement)
	30%
	12,11,370
	Within 7 days of acceptance

	Completion of Fieldwork (Month 6)
	30%
	12,11,370
	Within 15 days of fieldwork completion

	Submission of Draft Report (Month 10)
	25%
	10,09,475
	Within 15 days of draft submission

	Final Delivery & Conference Presentation (Month 12)
	15%
	6,05,685
	Within 15 days of final delivery


5. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) days from the date of issue. Beyond this period, rates may be revised to reflect changes in market conditions, exchange rates, or regulatory requirements in India Mumbai.
1. The Academic Researcher engaged shall be bound by a strict confidentiality and non-disclosure agreement. All raw data, preliminary findings, and unpublished manuscripts shall remain the exclusive intellectual property of the client institution.
1. All work shall be conducted in compliance with the University Grants Commission (UGC) guidelines, the Indian Council of Social Science Research (ICSSR) ethical standards, and the applicable provisions of the Indian Copyright Act, 1957.
1. Any change in scope, additional fieldwork locations beyond the 12 wards specified in India Mumbai, or extension of the project timeline shall be subject to a supplementary Quotation Estimate and mutual written consent.
1. Payment shall be made via bank transfer to the account designated in the service agreement. Late payments shall attract interest at the rate of 1.5% per month as per Indian commercial practice.
1. The Academic Researcher shall submit monthly progress reports to the client. A mid-project review meeting shall be conducted at the end of Month 6 at the client's premises in Mumbai.
1. This engagement is governed by the laws of India, and any disputes shall be subject to the exclusive jurisdiction of the competent courts in India Mumbai.
1. Taxes: All amounts are inclusive of applicable Goods and Services Tax (GST) as per the prevailing rates notified by the Government of India. TDS, if applicable, shall be deducted by the client as per the Income Tax Act, 1961.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and cost structure outlined herein for the engagement of the Academic Researcher for the specified research project in India Mumbai. This acceptance shall be deemed a formal order and shall trigger the execution of the detailed service agreement within seven (7) working days.
For and on behalf of the Client
Dr. Ananya Deshmukh
Head, Dept. of Social Sciences
Mumbai University, India Mumbai
Date: _______________
For and on behalf of the Service Provider
Prof. Rajiv Kulkarni
Director, Research & Consultancy Division
India Mumbai
Date: _______________
This Quotation Estimate is a confidential document intended solely for the named recipient. Unauthorized reproduction or distribution is prohibited.
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