# Quotation Estimate - Academic Researcher Services - Italy Naples

# QUOTATION ESTIMATE

Professional Academic Researcher Services — Italy Naples

Document Reference: QTE-NAP-2025-0472 | Validity: 60 Days from Issue Date

Prepared For:
Department of Humanities and Social Sciences
University of Naples Federico II
Via Chiaia, 35 — 80134 Naples, Italy

Prepared By:
Dr. Elena Marchetti, PhD
Independent Academic Researcher
Via Toledo, 112 — 80132 Naples, Italy
Email: e.marchetti@naplesresearch.it
VAT: IT01234567890

## 1. Purpose of This Quotation Estimate

This Quotation Estimate is issued to formally outline the scope, deliverables, and associated costs for the engagement of a qualified Academic Researcher to conduct a comprehensive literature review, qualitative fieldwork, and data analysis project commissioned by the University of Naples Federico II. The project is to be executed within the metropolitan area of Italy Naples, leveraging the region's rich archival resources, cultural institutions, and academic networks. This document serves as a binding cost proposal and shall remain valid for sixty (60) calendar days from the date of issue, after which all rates and conditions herein may be subject to revision.

## 2. Scope of Work — Academic Researcher Engagement

The Academic Researcher shall perform the following activities in support of the Department's ongoing research initiative on "Cultural Heritage Preservation in the Campania Region":

- Conduct a systematic literature review encompassing no fewer than 200 peer-reviewed sources published between 1990 and 2025, with a specific focus on Italian and Mediterranean cultural heritage scholarship.

- Perform on-site qualitative fieldwork at a minimum of twelve (12) heritage sites across Italy Naples and the surrounding provinces, including the Archaeological Park of Pompeii, the National Archaeological Museum of Naples, the Certosa di San Martino, and the historic centre of Naples (UNESCO World Heritage Site).

- Administer semi-structured interviews with no fewer than twenty-five (25) local stakeholders, including museum curators, municipal heritage officers, and community representatives in the Naples metropolitan area.

- Compile and analyse all collected data using mixed-methods approaches, producing a final research report of no fewer than 80 pages in English and Italian.

- Deliver a presentation of findings to the Department's faculty and invited external reviewers at the University of Naples Federico II, Campus di Via Cintia.

## 3. Itemised Cost Breakdown

| Item No. | Description of Service | Duration / Quantity | Unit Rate (EUR) | Subtotal (EUR) |
| --- | --- | --- | --- | --- |
| 01 | Literature review and bibliographic research (desk-based, conducted from Naples office) | 40 hours | €85.00 | €3,400.00 |
| 02 | On-site fieldwork and documentation at heritage sites in Italy Naples and Campania | 30 days | €420.00 | €12,600.00 |
| 03 | Stakeholder interviews, transcription, and thematic coding | 25 interviews | €180.00 | €4,500.00 |
| 04 | Data analysis, report writing, and bilingual (EN/IT) editing | 60 hours | €90.00 | €5,400.00 |
| 05 | Final presentation and dissemination workshop at University of Naples Federico II | 1 day | €1,200.00 | €1,200.00 |
| 06 | Travel, local transport, and site-access fees within the Naples metropolitan area | 30 days | €65.00 | €1,950.00 |
| 07 | Project management, progress reporting, and administrative coordination | 20 hours | €75.00 | €1,500.00 |
| TOTAL ESTIMATED COST (excl. VAT) |  |  |  | €30,550.00 |
| VAT (22% — Italian standard rate) |  |  |  | €6,721.00 |
| GRAND TOTAL (incl. VAT) |  |  |  | €37,271.00 |

## 4. Payment Terms

Payment shall be structured as follows: 30% advance payment upon acceptance of this Quotation Estimate; 40% upon completion of fieldwork and delivery of the interim report; and 30% upon final acceptance of the completed research report and presentation. All payments shall be made via bank transfer to the account details provided in the accompanying invoice. Late payments shall accrue interest at the rate of 1.5% per month in accordance with Italian commercial law (Codice Civile, Art. 1284).

## 5. Terms and Conditions

- This Quotation Estimate is non-binding until formally accepted in writing by the authorised representative of the University of Naples Federico II.

- All work shall be conducted in compliance with Italian data protection regulations (GDPR and D.Lgs. 196/2003) and the ethical guidelines of the Italian National Research Council (CNR).

- The Academic Researcher retains full intellectual property rights over original methodologies; however, all final reports, datasets, and publications produced under this engagement shall be jointly owned by the Researcher and the Commissioning Department.

- Any changes to the scope of work, including additional fieldwork sites beyond the twelve specified in Italy Naples, shall require a written amendment to this estimate and may result in adjusted costs.

- The project timeline is estimated at fourteen (14) weeks from the date of contract signature. Delays attributable to force majeure, institutional access restrictions, or public holidays in the Campania region shall extend the timeline proportionally.

- Disputes arising from this engagement shall be resolved through mediation in Naples, Italy, in accordance with the provisions of the Italian Code of Civil Procedure.

- This estimate does not include costs for third-party permissions, archival reproduction fees, or translation services beyond the bilingual report, which shall be billed separately if required.

## 6. Acceptance and Authorisation

By signing below, both parties acknowledge that they have read, understood, and agree to all terms set forth in this Quotation Estimate for the engagement of the Academic Researcher in the project described herein, to be carried out in Italy Naples.

For the Commissioning Party
University of Naples Federico II

Name: ____________________________
Title: ____________________________
Signature: ________________________
Date: ____________________________

For the Academic Researcher
Dr. Elena Marchetti, PhD

Name: Elena Marchetti
Title: Independent Academic Researcher
Signature: ________________________
Date: ____________________________

Quotation Estimate QTE-NAP-2025-0472 | Academic Researcher Services | Italy Naples | Page 1 of 1

This document is generated electronically and does not require a physical signature to be valid. For queries, contact e.marchetti@naplesresearch.it or +39 081 555 0142.