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	Quotation Estimate No.
	QEST-2025-0847

	Date of Issue
	15 June 2025

	Validity Period
	30 days from date of issue (15 July 2025)

	Client / Recipient
	Dr. Ayesha Khan, Department of Social Sciences, National University of Sciences and Technology (NUST), Pakistan Islamabad

	Project Title
	Comprehensive Academic Researcher Engagement for Multi-Disciplinary Study on Urban Development in Pakistan Islamabad

	Prepared By
	Muhammad Imran Siddiqui, Senior Accountant


1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by Scholarly Research & Consultancy Services (Pvt.) Ltd. to provide a detailed financial and operational breakdown for the engagement of a qualified Academic Researcher to support a multi-disciplinary research project focused on urban development, policy analysis, and socio-economic transformation in Pakistan Islamabad. This document serves as the official Quotation Estimate and outlines all deliverables, timelines, associated costs, and contractual obligations that will govern the professional relationship between our firm and the client institution based in Pakistan Islamabad.
2. Scope of Work – Academic Researcher Services
The Academic Researcher engaged under this Quotation Estimate will be responsible for the following activities, all conducted within the geographical and institutional context of Pakistan Islamabad:
· Conducting a comprehensive literature review spanning at least 200 peer-reviewed publications related to urban planning, public policy, and economic development specific to Pakistan Islamabad and comparable South Asian metropolitan regions.
· Designing and executing a mixed-methods research framework (quantitative surveys and qualitative interviews) targeting a minimum of 500 respondents across the ten union councils of Pakistan Islamabad.
· Performing statistical analysis using SPSS and R software, producing at least 15 analytical tables and 10 interpretive figures for the final research report.
· Drafting a 60-page research monograph suitable for submission to a Q1-indexed journal, with full adherence to APA 7th edition formatting standards.
· Delivering two (2) in-person presentation sessions at the client's campus in Pakistan Islamabad to present interim findings and final conclusions to the faculty review board.
· Providing ongoing advisory support for a period of three (3) months post-delivery to assist with peer-review revisions and conference abstract preparation.
3. Detailed Cost Breakdown – Quotation Estimate
	Item No.
	Description of Service
	Duration / Qty
	Unit Cost (PKR)
	Total (PKR)

	01
	Academic Researcher – Monthly Professional Fee (PhD-qualified, 10+ years experience in social sciences)
	6 months
	250,000
	1,500,000

	02
	Field Data Collection in Pakistan Islamabad (transport, enumerator stipends, printing of survey instruments)
	1 lot
	385,000
	385,000

	03
	Statistical Software Licensing (SPSS + R Studio, 6-month institutional license)
	1 lot
	95,000
	95,000

	04
	Academic Journal Publication Fee (Q1 journal, open-access APC)
	1 article
	420,000
	420,000

	05
	Two (2) Presentation Sessions in Pakistan Islamabad (venue coordination, AV setup, travel within Islamabad)
	2 sessions
	45,000
	90,000

	06
	Post-Delivery Advisory Support (3 months, remote + 2 in-person visits to Pakistan Islamabad)
	3 months
	120,000
	360,000

	07
	Project Management & Administrative Overhead (10% of subtotal)
	1 lot
	—
	285,000

	Subtotal (PKR)
	3,135,000

	GST @ 16% (as applicable under Pakistan tax regulations)
	501,600

	GRAND TOTAL (PKR)
	3,636,600


* All amounts are quoted in Pakistani Rupees (PKR). The above Quotation Estimate is exclusive of any additional costs that may arise from scope changes mutually agreed upon in writing.
4. Payment Terms
· Advance Payment (40%): PKR 1,454,640 – due within seven (7) working days of acceptance of this Quotation Estimate.
· Milestone Payment (35%): PKR 1,272,810 – due upon submission of the draft research monograph for client review.
· Final Payment (25%): PKR 909,150 – due within fourteen (14) days of final delivery and acceptance of all deliverables.
Payments shall be made via bank transfer to the account of Scholarly Research & Consultancy Services (Pvt.) Ltd., Meezan Bank, Blue Area Branch, Pakistan Islamabad. Account details are available upon request.
5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, all rates are subject to revision based on prevailing market conditions in Pakistan Islamabad.
· The Academic Researcher assigned to this project shall be a PhD-qualified professional with a minimum of ten years of post-doctoral research experience. The client reserves the right to review the researcher's CV prior to commencement.
· All intellectual property generated under this engagement shall be jointly owned by the client institution and our firm, as stipulated in the separate Memorandum of Understanding (MoU) to be executed in Pakistan Islamabad.
· Either party may terminate the engagement with thirty (30) days' written notice. In such an event, the client shall be liable for all costs incurred up to the date of termination as reflected in this Quotation Estimate.
· All work shall comply with the ethical guidelines of the Pakistan Council of Science and Technology (PCST) and the institutional research ethics committee of the client's university in Pakistan Islamabad.
· Confidentiality: The Academic Researcher and all supporting staff shall sign a Non-Disclosure Agreement (NDA) prior to accessing any proprietary data or unpublished findings.
· Disputes arising from this Quotation Estimate shall be resolved through arbitration in Pakistan Islamabad in accordance with the Arbitration Act, 1940 of Pakistan.
6. Deliverables and Timeline
	Milestone
	Deliverable
	Target Date

	M1
	Approved Literature Review & Research Design Document
	31 July 2025

	M2
	Field Data Collection Completed (Pakistan Islamabad)
	30 September 2025

	M3
	Statistical Analysis & Draft Monograph (60 pages)
	30 November 2025

	M4
	Final Presentation at Client Campus, Pakistan Islamabad
	15 December 2025

	M5
	Journal Submission & Post-Delivery Advisory Commencement
	31 January 2026


7. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and financial obligations outlined herein for the engagement of the Academic Researcher in Pakistan Islamabad.
For Scholarly Research & Consultancy Services (Pvt.) Ltd.
Name: Muhammad Imran Siddiqui
Title: Senior Accountant
Signature & Date
For the Client (NUST, Pakistan Islamabad)
Name: Dr. Ayesha Khan
Title: Head, Department of Social Sciences
Signature & Date
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