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1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by the East African Research & Consultancy Institute (EARCI) in Tanzania Dar es Salaam to provide a comprehensive, itemized financial breakdown for the engagement of a qualified Academic Researcher to conduct a multi-disciplinary study on community health outcomes and rural economic development across selected regions of Tanzania. This document serves as the official Quotation Estimate for all parties involved and outlines the full scope of services, associated costs, timelines, and contractual terms governing the engagement of the Academic Researcher in Tanzania Dar es Salaam.
2. Scope of Services – Academic Researcher Engagement
The Academic Researcher engaged under this Quotation Estimate shall perform the following duties and deliverables within the Tanzania Dar es Salaam operational framework:
	No.
	Service / Deliverable
	Duration
	Unit
	Cost (TZS)

	1
	Literature review and research design development by the Academic Researcher
	3 weeks
	Lump sum
	4,500,000

	2
	Field data collection – surveys, interviews, and focus groups in 4 districts of Tanzania Dar es Salaam region
	6 weeks
	Lump sum
	12,800,000

	3
	Quantitative and qualitative data analysis using SPSS and NVivo
	4 weeks
	Lump sum
	6,200,000

	4
	Preparation of interim progress report for client review
	1 week
	Lump sum
	1,800,000

	5
	Final research report (minimum 120 pages) with policy recommendations
	3 weeks
	Lump sum
	5,500,000

	6
	Academic Researcher travel and accommodation within Tanzania Dar es Salaam and surrounding districts
	17 weeks
	Monthly
	3,200,000

	7
	Publication support – formatting for peer-reviewed journal submission
	2 weeks
	Lump sum
	2,000,000

	8
	Project management, coordination, and administrative overhead
	Full project
	Lump sum
	3,000,000

	TOTAL ESTIMATED COST (TZS)
	41,000,000

	TOTAL ESTIMATED COST (USD – approximate at TZS 2,600/USD)
	15,769.23


3. Qualifications of the Academic Researcher
The Academic Researcher assigned to this project in Tanzania Dar es Salaam shall hold a minimum of a Doctorate (PhD) in a relevant social science, public health, or development studies discipline. The Academic Researcher must demonstrate a minimum of eight (8) years of post-doctoral research experience, a published record of at least fifteen (15) peer-reviewed articles, and prior experience conducting field research in East African contexts. All qualifications will be verified prior to commencement of work under this Quotation Estimate.
4. Payment Schedule
Payment for the services outlined in this Quotation Estimate shall be made in the following tranches, payable to the EARCI account at National Bank of Commerce, Tanzania Dar es Salaam branch:
1. 30% (TZS 12,300,000) – Upon signing of the engagement contract and submission of the approved research design by the Academic Researcher.
1. 40% (TZS 16,400,000) – Upon successful completion of field data collection and submission of the interim progress report.
1. 25% (TZS 10,250,000) – Upon delivery of the final research report and acceptance by the client.
1. 5% (TZS 2,050,000) – Upon completion of publication support and final project close-out.
5. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, all costs are subject to revision due to market fluctuations in Tanzania Dar es Salaam.
1. All prices are quoted in Tanzanian Shillings (TZS) and are inclusive of applicable Value Added Tax (VAT) at the prevailing rate of 18% as mandated by the Tanzania Revenue Authority.
1. The Academic Researcher shall adhere to all ethical guidelines set forth by the National Institute for Medical Research (NIMR) and the Tanzania Commission for Science and Technology (COSTECH).
1. Intellectual property rights for all research outputs shall be jointly held by the client and EARCI, as stipulated in the master service agreement.
1. Any changes to the scope of work must be documented in a formal amendment to this Quotation Estimate and signed by both parties before additional work commences.
1. Disputes arising from this engagement shall be resolved through arbitration in Tanzania Dar es Salaam in accordance with the Arbitration Act, Cap. 20, Laws of Tanzania.
1. The Academic Researcher shall maintain full professional confidentiality regarding all data collected, particularly sensitive community health information gathered in Tanzania Dar es Salaam and its surrounding regions.
6. Project Timeline
The total estimated duration for the Academic Researcher engagement under this Quotation Estimate is seventeen (17) weeks, commencing on 1 August 2025 and concluding by 21 November 2025, subject to client approval and regulatory clearances obtained in Tanzania Dar es Salaam.
7. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and financial obligations outlined herein for the engagement of the Academic Researcher in Tanzania Dar es Salaam.
For and on behalf of EARCI (Provider)
Name: Dr. Amina M. Hassan
Title: Lead Academic Researcher
Date: ______________________
For and on behalf of the Client
Name: ______________________
Title: ______________________
Date: ______________________
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