# Quotation Estimate - Academic Researcher Services - United States Chicago

# QUOTATION ESTIMATE

Professional Academic Researcher Services — United States Chicago

Document Reference: QE-CHI-2025-04782 | Issued: June 12, 2025

Prepared By:
Meridian Research Consulting Group
1418 N. Lake Shore Drive, Suite 720
Chicago, Illinois 60610
United States
Phone: (312) 555-0187
Email: estimates@meridianresearch-chi.com

Prepared For:
Dr. Eleanor Whitfield, Ph.D.
Department of Social Sciences
University of Chicago
5801 S. Ellis Avenue
Chicago, Illinois 60637
United States
Phone: (773) 555-0342
Email: e.whitfield@uchicago.edu

1. SCOPE OF SERVICES — Academic Researcher Engagement

This Quotation Estimate is issued by Meridian Research Consulting Group to formally outline the professional services to be rendered by a qualified Academic Researcher engaged on behalf of the client. The scope of work described herein pertains to a comprehensive research engagement to be conducted within the metropolitan area of United States Chicago, encompassing fieldwork, data collection, literature synthesis, and analytical reporting. The Academic Researcher assigned to this project holds a Doctoral degree in the relevant discipline and possesses a minimum of eight years of peer-reviewed publication experience. All deliverables will conform to the academic standards expected by institutions operating in the United States Chicago higher education and research ecosystem.

2. LINE-ITEM COST BREAKDOWN

| # | Service Description | Duration / Qty | Unit Rate (USD) | Subtotal (USD) | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Initial literature review and research design consultation conducted by the Academic Researcher | 2 weeks | $4,200.00 | $8,400.00 | Includes 3 in-person meetings in Chicago, IL |
| 2 | Field data collection and participant interviews within the United States Chicago metropolitan area | 6 weeks | $5,800.00 | $34,800.00 | Covers travel within Cook County and surrounding suburbs |
| 3 | Quantitative and qualitative data analysis using SPSS, NVivo, and R statistical software | 4 weeks | $6,500.00 | $26,000.00 | Performed by the Academic Researcher and one graduate assistant |
| 4 | Drafting of the comprehensive research report (minimum 60 pages) with full APA 7th edition formatting | 3 weeks | $7,200.00 | $21,600.00 | Two revision cycles included |
| 5 | Peer review coordination and editorial support for journal submission preparation | 2 weeks | $3,900.00 | $7,800.00 | Target journals in the Chicago academic circuit |
| 6 | Project management, scheduling, and administrative oversight by the Academic Researcher lead | 27 weeks (full project) | $1,100.00 | $29,700.00 | Weekly progress reports to client |
| 7 | Access to Chicago-area university libraries, databases, and archival materials (subscription fees) | 27 weeks | $450.00 | $12,150.00 | Includes JSTOR, ProQuest, and local archive fees |
| 8 | Contingency and miscellaneous expenses (printing, participant incentives, software licenses) | Flat fee | $1.00 | $5,550.00 | Subject to client approval for items over $500 |
| TOTAL ESTIMATED COST (USD): |  |  |  | $145,000.00 |  |

Note: This Quotation Estimate is valid for a period of sixty (60) calendar days from the date of issue. All rates are quoted in United States Dollars (USD) and are inclusive of applicable Illinois state and Chicago municipal sales tax where legally required. The Academic Researcher engagement is subject to a signed Master Service Agreement prior to commencement of work.

3. TERMS AND CONDITIONS

3.1 Payment Schedule: Payment shall be rendered in four equal installments of $36,250.00, due at project initiation, at the 25% completion milestone, at the 50% completion milestone, and upon final delivery of all deliverables. Late payments shall accrue interest at a rate of 1.5% per month, consistent with commercial practices in United States Chicago.

3.2 Intellectual Property: All research outputs, including but not limited to datasets, analytical models, and written reports produced by the Academic Researcher, shall become the sole property of the client upon full and final payment. The Academic Researcher retains the right to reference the engagement in professional portfolios and academic CVs, subject to the client's written consent regarding publication of specific findings.

3.3 Confidentiality: The Academic Researcher and all supporting personnel shall adhere to a strict Non-Disclosure Agreement (NDA) in compliance with the Illinois Freedom of Information Act and applicable federal research data protection regulations. All participant data collected in the United States Chicago area shall be anonymized and stored in accordance with IRB-approved protocols.

3.4 Cancellation and Termination: Either party may terminate this engagement with thirty (30) days written notice. In the event of client-initiated cancellation, all work completed to date shall be invoiced at the rates specified in this Quotation Estimate. The Academic Researcher reserves the right to withdraw from the engagement if payment terms are not met within fifteen (15) business days of invoice date.

3.5 Governing Law: This Quotation Estimate and any resulting contractual obligations shall be governed by and construed in accordance with the laws of the State of Illinois, United States. Any disputes shall be resolved through binding arbitration in Chicago, Illinois, in accordance with the rules of the American Arbitration Association.

3.6 Limitation of Liability: Meridian Research Consulting Group and the assigned Academic Researcher shall not be liable for indirect, incidental, or consequential damages arising from the performance of services described in this estimate. Total liability shall not exceed the total amount paid under this Quotation Estimate.

4. ACCEPTANCE AND AUTHORIZATION

By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the engagement of the Academic Researcher services in United States Chicago. This document does not constitute a binding contract until a formal Master Service Agreement is executed by both parties.

Prepared By (Vendor):

______________________________
Marcus T. Delaney, M.B.A.
Director of Research Operations
Meridian Research Consulting Group
Date: _______________

Accepted By (Client):

______________________________
Dr. Eleanor Whitfield, Ph.D.
Principal Investigator
University of Chicago
Date: _______________

Meridian Research Consulting Group — 1418 N. Lake Shore Drive, Suite 720, Chicago, IL 60610, United States

Quotation Estimate Reference: QE-CHI-2025-04782 | This document is confidential and intended solely for the named recipient.

© 2025 Meridian Research Consulting Group. All rights reserved.