# Quotation Estimate - Academic Researcher Services - Houston, United States

# Meridian Academic Consulting Group

4500 Post Oak Boulevard, Suite 1200, Houston, Texas 77056, United States

Phone: (713) 555-0187 | Email: estimates@meridianacademic.com

Texas Business License No. TX-2024-88431 | EIN: 74-XXXXXXX

Quotation Estimate

### Quotation Details

Quotation No.: QTE-HOU-2025-0472

Date Issued: June 12, 2025

Valid Until: July 12, 2025

Prepared By: Dr. Eleanor Whitfield, Director of Research Services

### Client Information

Client: University of Houston Graduate Research Division

Address: 4800 Calhoun Road, Houston, TX 77204, United States

Contact: Prof. Marcus Delgado, Department Chair

Project Ref: UH-GRD-2025-119

## Scope of Services

This Quotation Estimate is prepared for the engagement of a qualified Academic Researcher to conduct a multi-phase literature review, data analysis, and peer-reviewed publication support project on behalf of the University of Houston Graduate Research Division. All services described herein will be performed within the greater United States Houston metropolitan area, with primary work conducted at the client's facilities located in the Rice University corridor of Houston, Texas. The Academic Researcher assigned to this engagement will hold a minimum of a Ph.D. in the relevant discipline and will possess no fewer than five years of postdoctoral research experience in the United States academic system.

## Itemized Cost Breakdown

| Item No. | Description of Service | Duration | Rate | Amount (USD) |
| --- | --- | --- | --- | --- |
| 01 | Academic Researcher – Senior Research Associate (Ph.D.) – Literature Review & Theoretical Framework Development | 6 weeks | $145/hr | $27,840.00 |
| 02 | Academic Researcher – Data Collection & Fieldwork Coordination in Houston, United States | 8 weeks | $130/hr | $41,600.00 |
| 03 | Statistical Analysis & Quantitative Modeling (SPSS, R, Stata) | 4 weeks | $155/hr | $24,800.00 |
| 04 | Manuscript Drafting, Peer Review Preparation & Journal Submission Support | 5 weeks | $140/hr | $22,400.00 |
| 05 | Project Management, Weekly Progress Reporting & Client Meetings (Houston, TX) | 23 weeks | $95/hr | $17,480.00 |
| 06 | Travel & Local Transportation within United States Houston Metro Area | 23 weeks | Flat | $3,200.00 |
| 07 | Software Licenses, Database Access (JSTOR, Scopus, Web of Science) & Research Materials | 23 weeks | Flat | $4,580.00 |
| 08 | Contingency & Administrative Overhead (8%) | — | — | $8,407.84 |
| TOTAL ESTIMATED COST (Before Applicable Texas Sales Tax) |  |  |  | $150,307.84 |

## Payment Schedule

This Quotation Estimate outlines the following payment milestones, all payable via ACH transfer or certified check to Meridian Academic Consulting Group, Houston, Texas:

- Milestone 1 (25%): $37,576.96 – Due upon execution of the Service Agreement and commencement of the project.

- Milestone 2 (30%): $45,092.35 – Due upon completion of the Literature Review and Theoretical Framework (Week 6).

- Milestone 3 (30%): $45,092.35 – Due upon delivery of the Statistical Analysis Report (Week 18).

- Milestone 4 (15%): $22,546.18 – Due upon final manuscript delivery and journal submission (Week 23).

## Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, all rates and availability of the Academic Researcher are subject to re-evaluation.

- All services will be rendered in compliance with the academic integrity standards of the United States higher education system and the specific institutional policies of the client located in Houston, Texas.

- The Academic Researcher shall maintain full confidentiality of all proprietary data, unpublished findings, and institutional information encountered during the engagement in the United States Houston area.

- Any scope changes exceeding ten percent (10%) of the original estimated hours will require a written amendment to this Quotation Estimate signed by both parties.

- Applicable Texas state and federal taxes, including but not limited to the 8.25% Harris County sales tax, will be added to the final invoice where legally required.

- Intellectual property produced under this engagement shall be jointly owned by the client and Meridian Academic Consulting Group, as stipulated in the separate Service Agreement.

- Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through binding arbitration in Houston, Texas, in accordance with the rules of the American Arbitration Association.

## Acceptance and Authorization

By signing below, both parties acknowledge and agree to the terms, conditions, and cost estimates set forth in this Quotation Estimate for the engagement of the Academic Researcher in the United States Houston region.

For Meridian Academic Consulting Group

Dr. Eleanor Whitfield, Director

Date: ______________________

For University of Houston Graduate Research Division

Prof. Marcus Delgado, Department Chair

Date: ______________________

Meridian Academic Consulting Group | 4500 Post Oak Blvd, Suite 1200, Houston, TX 77056, United States

Quotation Estimate No. QTE-HOU-2025-0472 | This document is a non-binding estimate unless countersigned by both parties.

© 2025 Meridian Academic Consulting Group. All rights reserved.