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QUOTATION ESTIMATE
Aerospace Engineer Professional Services — Iraq Baghdad
Meridian Aerospace Consulting Group • Office 12, Al-Mansour Business District, Baghdad, Iraq
	Quotation Estimate No.
	QTE-2025-BA-0472

	Date of Issue
	14 June 2025

	Valid Until
	14 July 2025 (30 calendar days)

	Prepared For
	Ministry of Industry and Mineral Resources, Republic of Iraq — Baghdad Headquarters

	Prepared By
	Dr. Khalid Al-Rashid, Lead Aerospace Engineer, P.E. (Iraqi Engineering Board Reg. No. AE-2019-0334)

	Project Location
	Baghdad, Iraq — Al-Rusafa Industrial Zone & Adjacent Airfields

	Currency
	US Dollars (USD)


1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is issued by Meridian Aerospace Consulting Group in response to the formal request for professional services from the Ministry of Industry and Mineral Resources, Republic of Iraq. The scope encompasses the full engagement of a qualified Aerospace Engineer to deliver design review, structural analysis, systems integration oversight, and technical advisory services for the modernization of Iraq’s domestic aviation infrastructure and light aerospace manufacturing facilities located in and around Iraq Baghdad. All pricing, deliverables, and timelines presented in this Quotation Estimate are binding upon acceptance and are subject to the terms and conditions outlined in Section 7 below.
2. Detailed Scope of Aerospace Engineer Services
The Aerospace Engineer assigned to this project will operate primarily out of the Baghdad office and will conduct on-site inspections at the Al-Rusafa Industrial Zone, the Othman airfield maintenance hangars, and the technical training campus in Al-Mansour. The Aerospace Engineer’s responsibilities include, but are not limited to: aerodynamic performance audits of existing fleet components; structural fatigue analysis of airframe sections; propulsion system compliance reviews against ICAO and Iraqi Civil Aviation Authority (ICAA) standards; and the preparation of engineering reports in both English and Arabic for submission to Iraqi regulatory bodies.
3. Itemized Cost Breakdown
	Ref.
	Description of Aerospace Engineer Service
	Duration / Qty
	Unit Rate (USD)
	Amount (USD)

	3.1
	Initial site survey and condition assessment of aerospace components at Iraq Baghdad facilities. Includes drone-based photogrammetry and NDT (Non-Destructive Testing) of primary structures.
	10 working days
	1,850.00
	18,500.00

	3.2
	Aerodynamic and structural analysis using FEA (Finite Element Analysis) software. The Aerospace Engineer will model load paths, stress concentrations, and fatigue life for three (3) airframe variants.
	25 working days
	2,200.00
	55,000.00

	3.3
	Propulsion system review and compliance documentation. The Aerospace Engineer will verify engine performance data against ICAO Annex 14 and ICAA Technical Regulation No. 7/2023.
	15 working days
	2,400.00
	36,000.00

	3.4
	Systems integration oversight for the new avionics upgrade programme. Includes interface control documents, wiring harness reviews, and electromagnetic compatibility (EMC) test supervision in Iraq Baghdad.
	30 working days
	2,600.00
	78,000.00

	3.5
	Preparation of final engineering reports, certification support packages, and a 12-month post-delivery technical advisory retainer. All documents will be bilingual (English/Arabic).
	20 working days + 12 months
	1,950.00
	39,000.00

	3.6
	Travel, local transportation, and per diem for the Aerospace Engineer and two (2) support technicians within Iraq Baghdad and surrounding governorates (Babil, Diyala).
	100 working days
	320.00
	32,000.00

	3.7
	Specialized testing equipment rental (ultrasonic flaw detectors, strain gauge sets, wind-tunnel time at partner facility in Erbil).
	Lump sum
	1.00
	22,500.00

	Subtotal
	281,000.00

	VAT / Iraqi Tax (0% — professional services exemption per Iraqi Tax Law 2014, Art. 42)
	0.00

	TOTAL QUOTATION ESTIMATE AMOUNT
	281,000.00


4. Project Timeline
The Aerospace Engineer engagement is scheduled to commence within fifteen (15) calendar days of written acceptance of this Quotation Estimate. The total project duration is estimated at one hundred and five (105) working days, followed by a twelve-month advisory retainer. A detailed Gantt chart and milestone schedule will be provided as an appendix upon contract execution. All critical deliverables will be submitted to the Iraq Baghdad project office no later than the dates specified in the approved schedule.
5. Qualifications of the Aerospace Engineer
The lead Aerospace Engineer, Dr. Khalid Al-Rashid, holds a Ph.D. in Aerospace Engineering from the University of Baghdad (2008), a Master’s in Aeronautical Structures from Cranfield University, UK (2004), and is a registered Professional Engineer with the Iraqi Engineering Board. He has over eighteen (18) years of experience in civil and military aerospace programmes, including structural certification for the Iraqi Air Force C-130 fleet and design consultancy for regional UAV manufacturers. His support team comprises two (2) certified aerospace technicians and one (1) Arabic-speaking technical writer based in Iraq Baghdad.
6. Payment Schedule
· Milestone 1 (25%): USD 70,250.00 — Due upon signed acceptance of this Quotation Estimate and commencement of the site survey phase.
· Milestone 2 (30%): USD 84,300.00 — Due upon delivery and client approval of the FEA structural analysis reports (Item 3.2).
· Milestone 3 (25%): USD 70,250.00 — Due upon completion of propulsion compliance and avionics integration oversight (Items 3.3 & 3.4).
· Milestone 4 (20%): USD 56,200.00 — Due upon submission of final engineering reports and commencement of the advisory retainer (Item 3.5).
All payments shall be made via wire transfer to the account of Meridian Aerospace Consulting Group, Bank of Baghdad, Al-Mansour Branch, in US Dollars. Invoices will be issued in duplicate (English and Arabic) and are payable within thirty (30) days of receipt.
7. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After expiry, all rates are subject to revision.
· The Aerospace Engineer shall comply with all applicable Iraqi laws, ICAA regulations, and site safety protocols at all Iraq Baghdad work locations.
· Intellectual property generated under this engagement shall be jointly owned by the client and Meridian Aerospace Consulting Group, with full disclosure rights to the Iraqi Ministry of Industry and Mineral Resources.
· Force majeure events, including but not limited to security disruptions in Iraq Baghdad, shall extend project timelines on a day-for-day basis without penalty to either party.
· Any change in scope beyond the items listed in Section 3 shall be documented in a formal Change Order signed by both parties before additional work commences.
· This Quotation Estimate does not constitute a contract until countersigned by both parties and the first milestone payment is received.
Note: This Quotation Estimate is prepared exclusively for the Ministry of Industry and Mineral Resources, Republic of Iraq, and is not transferable to any third party. All figures are in US Dollars and are exclusive of any costs arising from scope changes not explicitly stated herein.
8. Acceptance and Authorization
By signing below, the undersigned parties acknowledge and accept the terms, conditions, pricing, and scope of work as detailed in this Quotation Estimate for Aerospace Engineer services to be delivered in Iraq Baghdad.
For Meridian Aerospace Consulting Group
Dr. Khalid Al-Rashid
Lead Aerospace Engineer
Date: _______________
For the Ministry of Industry and Mineral Resources, Iraq
Authorized Signatory
Baghdad Headquarters
Date: _______________
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