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Quotation Reference
Ref: QTE-2025-BRU-0472
Date Issued: 14 June 2025
Valid Until: 14 September 2025
Currency: EUR (€)
Client Details
Client: M. Jean-Pierre Vandenberghe
Address: 45 Avenue Louise, 1050 Brussels, Belgium
Project Location: Ixelles, 1050 Brussels, Belgium
Contact: +32 470 123 456
1. Introduction & Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by Atelier Architectural Brussels, a registered Architect practice operating under the professional regulations of the Belgian Federal Service for Health, Food Chain and Environment (FOD), to provide a comprehensive and transparent cost breakdown for architectural services to be delivered in Belgium Brussels. This document serves as a binding estimate of fees, timelines, and deliverables associated with the proposed architectural project located in the municipality of Ixelles, within the Brussels-Capital Region of Belgium.
As a licensed Architect registered with the Brussels-Capital Region's Order of Architects, our firm is bound by the professional code of conduct established under Belgian law (Royal Decree of 25 March 1964 on the profession of Architect). This Quotation Estimate reflects the standard fee structure applicable to architectural engagements in Belgium Brussels, adjusted for the specific scope, complexity, and regulatory requirements of the proposed project.
2. Scope of Architectural Services
The Architect services outlined in this Quotation Estimate encompass the full design and coordination process for a residential renovation and extension project in Belgium Brussels. The scope includes, but is not limited to, the following phases:
· Phase A – Feasibility & Site Analysis: Preliminary assessment of the existing structure, topographical survey review, and compliance check against the Brussels-Capital Region's Urban Planning Code (Code de l'Aménagement du Territoire et de l'Urbanisme – CATU).
· Phase B – Conceptual Design: Development of architectural concept drawings, massing studies, and preliminary material specifications tailored to the heritage-sensitive context of the Brussels neighbourhood.
· Phase C – Detailed Design & Permit Application: Production of full construction drawings, structural coordination, energy performance calculations (PEB – Performance Énergétique du Bâtiment), and preparation of the complete building permit dossier for submission to the Brussels-Capital Region's Urban Planning Department.
· Phase D – Tender & Contract Administration: Preparation of technical specifications, coordination of contractor tenders, and issuance of the construction contract in accordance with Belgian construction law.
· Phase E – Construction Supervision: On-site architectural supervision, progress inspections, quality control, and final acceptance documentation throughout the construction period in Belgium Brussels.
3. Itemized Cost Breakdown
	Item No.
	Description of Architect Service
	Duration
	Estimated Cost (EUR)

	01
	Feasibility study, site survey review, and CATU compliance assessment for the Brussels project site
	3 weeks
	€ 4,200.00

	02
	Conceptual architectural design, 3D visualisations, and client presentation sessions (3 iterations)
	5 weeks
	€ 8,750.00

	03
	Detailed construction drawings, structural engineering coordination, and PEB energy calculations
	8 weeks
	€ 14,300.00

	04
	Building permit dossier preparation and submission to the Brussels-Capital Region Urban Planning Authority
	4 weeks
	€ 3,800.00

	05
	Tender document preparation, contractor coordination, and construction contract drafting
	4 weeks
	€ 5,600.00

	06
	On-site architectural supervision, bi-weekly progress inspections, and quality assurance (estimated 14-month construction period)
	14 months
	€ 22,400.00

	07
	Final as-built documentation, handover certificates, and warranty period support (12 months post-completion)
	12 months
	€ 3,200.00

	08
	Statutory professional liability insurance (RC Professionnelle) – annual premium allocation
	24 months
	€ 1,150.00

	Subtotal (Architect Professional Fees)
	€ 63,400.00

	VAT (TVA) at 21% – applicable rate for architectural services in Belgium
	€ 13,314.00

	TOTAL ESTIMATED COST (Incl. VAT)
	€ 76,714.00


4. Payment Schedule
In accordance with standard practice for Architect engagements in Belgium Brussels, the total fees set forth in this Quotation Estimate shall be invoiced and paid according to the following milestone-based schedule:
· 10% upon signing of the Architect's engagement contract (€ 7,671.40)
· 15% upon completion of Phase B – Conceptual Design approval (€ 11,507.10)
· 25% upon submission of the building permit application to the Brussels-Capital Region (€ 19,178.50)
· 20% upon grant of the building permit and commencement of construction (€ 15,342.80)
· 25% during the construction supervision period, invoiced monthly (€ 19,178.50)
· 5% upon final handover and completion of as-built documentation (€ 3,835.70)
5. Terms & Conditions
1. This Quotation Estimate is valid for a period of ninety (90) calendar days from the date of issue. Beyond this period, the Architect reserves the right to revise fees to reflect current market conditions in Belgium Brussels.
1. All fees are quoted in Euros (EUR) and are inclusive of the Architect's professional time, standard software licensing, and routine administrative costs. Travel expenses beyond the Brussels-Capital Region boundary shall be invoiced separately at the Belgian government-approved rate.
1. The Architect shall maintain professional liability insurance (RC Professionnelle) with a minimum coverage of € 1,000,000 per claim, as mandated by Belgian professional regulations for architects practising in Belgium Brussels.
1. Any changes to the project scope, additional design iterations beyond the three included in Phase B, or extensions to the construction supervision period shall be subject to a supplementary Quotation Estimate issued by the Architect prior to execution.
1. This engagement is governed by the laws of the Kingdom of Belgium. Any disputes arising from this Quotation Estimate or the subsequent Architect's contract shall be submitted to the competent courts of Brussels, Belgium.
1. The Architect shall comply with all applicable building regulations, energy performance standards (PEB), and urban planning directives issued by the Brussels-Capital Region and the municipality of Ixelles.
1. Confidentiality: All project documentation, drawings, and client information shall be treated as strictly confidential in accordance with the Belgian Data Protection Act and GDPR regulations.
6. Acceptance & Signatures
By signing below, the Client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and fee structure set forth herein for the Architect services to be performed in Belgium Brussels. This signature constitutes a formal acceptance of the estimate and authorises the Architect to proceed with Phase A of the project.
For and on behalf of the Architect:
Atelier Architectural Brussels
Name: Arch. Marie-Claire De Smet, M.Arch.
Registration No.: BRU-2003-0847
Signature & Date: ___________________________
For and on behalf of the Client:
Name: M. Jean-Pierre Vandenberghe
Address: 45 Avenue Louise, 1050 Brussels
Signature & Date: ___________________________
Atelier Architectural Brussels – Licensed Architect Practice – Brussels-Capital Region, Belgium
This Quotation Estimate (Ref: QTE-2025-BRU-0472) is issued in duplicate. One copy for the Architect's records, one copy for the Client.
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