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QUOTATION ESTIMATE
Professional Architect Services — Santiago, Chile
Quotation Reference: QTE-SCL-2025-04782
ARCHITECT SERVICES • CHILE SANTIAGO
Issued By (Architect Firm)
Estudio Arquitectónico Andes Patagonia SpA
Address: Av. Apoquindo 4501, Of. 1203, Las Condes
Santiago, Región Metropolitana, Chile
RUT: 76.543.210-K
Phone: +56 2 2345 6789
Email: proyectos@andespatagonia.cl
Architect in Charge: Arq. María Fernanda Rojas, M.Arch.
Prepared For (Client)
Constructora del Pacífico Limitada
Address: Av. Providencia 1850, Piso 8
Providencia, Santiago, Chile
RUT: 78.912.345-6
Contact: Sr. Carlos Mendoza, Gerente de Proyectos
Phone: +56 9 8765 4321
Email: cmendoza@constructorapacifico.cl
Date of Issue: 15 June 2025
Quotation Validity: 30 calendar days from issue date
Project Location: Santiago, Chile (Región Metropolitana)
Project Type: Residential & Commercial Mixed-Use Development
Estimated Area: 4,200 m² (Santiago, Chile)
Payment Currency: Chilean Pesos (CLP)
1. Scope of Architect Services — Santiago, Chile
This Quotation Estimate is issued by Estudio Arquitectónico Andes Patagonia SpA to formally present the professional fees and associated costs for the full range of Architect services required for the design, development, and construction supervision of the mixed-use residential and commercial project located in the commune of Las Condes, Santiago, Chile. The Architect firm shall be responsible for all phases of architectural design in compliance with the Chilean Building Code (Código de la Construcción), the local urban planning regulations of the Metropolitan Region, and the specific zoning ordinances of the municipality of Santiago.
2. Itemized Quotation Estimate Breakdown
	N°
	Architect Service Description
	Phase / Stage
	Duration
	Amount (CLP)
	VAT 19%

	1
	Feasibility Study & Site Analysis in Santiago, Chile (topography, solar orientation, wind patterns, urban context)
	Pre-Design
	3 weeks
	1,850,000
	351,500

	2
	Conceptual Architect Design — massing studies, volumetric proposals, and preliminary floor plans for the 4,200 m² development
	Concept Design
	5 weeks
	4,200,000
	798,000

	3
	Schematic Design Development — detailed architectural drawings, material palettes, and structural coordination for Santiago, Chile compliance
	Schematic Design
	6 weeks
	5,600,000
	1,064,000

	4
	Design Development & Technical Documentation — full set of construction drawings, specifications, and technical memos per Chilean regulations
	Design Development
	8 weeks
	7,800,000
	1,482,000

	5
	Construction Documentation & Permitting Package — preparation and submission of all documents to the Seremi de Vivienda y Urbanismo and the Municipalidad de Santiago for building permit (Permiso de Edificación)
	Documentation
	6 weeks
	4,500,000
	855,000

	6
	Construction Administration & Site Supervision — weekly site visits in Santiago, Chile, progress inspections, and coordination with contractors
	Construction Phase
	18 months
	12,400,000
	2,356,000

	7
	Interior Architect Design — common areas, lobby, commercial ground floor, and amenity spaces
	Interior Design
	4 weeks
	3,200,000
	608,000

	8
	Landscape & Urban Integration Plan — green areas, pedestrian pathways, and integration with the Santiago, Chile urban fabric
	Landscape
	3 weeks
	2,100,000
	399,000

	9
	Energy Efficiency & Sustainability Certification Support (LEED / Chilean Green Building Standard)
	Sustainability
	4 weeks
	1,950,000
	370,500

	10
	Final As-Built Documentation & Project Handover Package
	Closeout
	3 weeks
	1,200,000
	228,000

	SUBTOTAL (Architect Professional Fees)
	44,800,000
	8,512,000

	TOTAL QUOTATION ESTIMATE (incl. VAT 19%)
	53,312,000 CLP


3. Payment Schedule
This Quotation Estimate for Architect services in Santiago, Chile shall be paid according to the following milestone-based schedule:
	Milestone
	Percentage
	Amount (CLP, incl. VAT)

	Contract signing & mobilization
	15%
	7,996,800

	Concept Design approval
	15%
	7,996,800

	Schematic Design approval
	15%
	7,996,800

	Design Development & Permit submission
	20%
	10,662,400

	Construction supervision (monthly installments over 18 months)
	25%
	13,328,000

	Final handover & as-built delivery
	10%
	5,331,200


4. Terms & Conditions of this Quotation Estimate
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, the Architect firm reserves the right to revise pricing due to market conditions in Santiago, Chile.
1. All amounts are expressed in Chilean Pesos (CLP) and include the applicable 19% Value Added Tax (IVA) as established by the Servicio de Impuestos Nacionales of Chile.
1. The Architect firm shall comply with all professional standards set by the Colegio de Arquitectos de Chile and the regulations of the Superintendencia de Construcción y Vivienda (SERVICIO).
1. Any changes to the scope of Architect services beyond the parameters described in this Quotation Estimate shall be subject to a supplementary agreement and additional cost assessment.
1. The project location is strictly within the administrative boundaries of Santiago, Chile (Región Metropolitana). Travel to sites outside this area will be billed separately.
1. Intellectual property of all Architect designs, drawings, and documentation produced under this Quotation Estimate shall remain with the Architect firm until full payment is received.
1. Disputes arising from this Quotation Estimate shall be resolved under the civil jurisdiction of the courts of Santiago, Chile, in accordance with the Chilean Civil Code.
1. The Architect firm carries professional liability insurance (Seguro de Responsabilidad Civil Profesional) with a coverage of no less than 50,000,000 CLP, valid throughout the project duration in Santiago, Chile.
5. Acceptance & Authorization
By signing below, the Client acknowledges receipt of this Quotation Estimate for Architect services in Santiago, Chile, and authorizes Estudio Arquitectónico Andes Patagonia SpA to proceed with the project upon execution of the formal professional services contract.
For the Architect Firm
Arq. María Fernanda Rojas
Director & Lead Architect
Estudio Arquitectónico Andes Patagonia SpA
Santiago, Chile
For the Client
Sr. Carlos Mendoza
Gerente de Proyectos
Constructora del Pacífico Limitada
Santiago, Chile
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This document is a formal Quotation Estimate for professional Architect services and does not constitute a binding contract until both parties execute the definitive agreement.
