Quotation Estimate - Architect Services - DR Congo Kinshasa
Quotation Estimate
Professional Architect Services — Democratic Republic of Congo, Kinshasa
Quotation Reference: QTE-KIN-2025-0472
Date of Issue: 15 June 2025
Valid Until: 15 September 2025
Prepared By: Studio Kongo Architectes
Address: Avenue de la Paix, Gombe
Kinshasa, DR Congo
Contact: +243 990 000 000
1. Client Information
	Client Name:
	Société ImmoKin SA

	Project Location:
	Commune de Lemba, Kinshasa, DR Congo

	Project Type:
	Residential & Commercial Mixed-Use Development (12,500 m²)

	Architect of Record:
	Ing. Mireille Kabasele, RAI (République de l’Afrique)


2. Scope of Architect Services
This Quotation Estimate is issued by Studio Kongo Architectes to provide a comprehensive and transparent breakdown of all professional Architect fees and associated costs for the design, planning, and supervisory services required for the above-referenced development project located in Kinshasa, DR Congo. The Architect shall deliver all services in full compliance with the National Building Code of the Democratic Republic of Congo, the urban planning regulations of the Commune de Lemba, and the applicable standards of the Ordre des Architectes de la République Démocratique du Congo (OARDC).
2.1 Phase I — Pre-Design & Feasibility (Weeks 1–6)
The Architect will conduct a full site survey in Kinshasa, assess soil conditions specific to the Congolese riverine terrain, review existing urban zoning maps issued by the Direction Provinciale de l’Urbanisme, and prepare a feasibility report. This phase includes two (2) client consultation meetings held at the project site in Lemba, Kinshasa.
2.2 Phase II — Schematic Design (Weeks 7–14)
The Architect will produce schematic design drawings, massing studies, and preliminary architectural renderings. All designs will incorporate passive cooling strategies appropriate to the tropical climate of Kinshasa, DR Congo, and will respect the cultural and aesthetic context of the surrounding neighbourhood.
2.3 Phase III — Design Development & Permitting (Weeks 15–26)
The Architect will develop detailed architectural drawings, structural coordination documents, and MEP (Mechanical, Electrical, Plumbing) layouts. The Architect will also prepare and submit the full building permit application to the Commune de Lemba authorities in Kinshasa and manage all regulatory approvals required under DR Congo construction law.
2.4 Phase IV — Construction Documents (Weeks 27–36)
Complete set of construction-ready drawings, specifications, and bill of quantities. The Architect will coordinate with local contractors in Kinshasa to ensure constructability and material availability within the DR Congo supply chain.
2.5 Phase V — Construction Administration & Supervision (Weeks 37–120)
The Architect will provide on-site supervision at the Kinshasa project location, conduct weekly progress inspections, review shop drawings, issue construction change orders, and certify payment applications. The Architect will maintain a permanent liaison with the client and the DR Congo municipal inspection office throughout the construction period.
3. Itemized Cost Breakdown
	Item No.
	Description of Architect Service
	Duration
	Cost (USD)

	01
	Pre-Design & Feasibility Study — Site survey, zoning review, client consultations in Kinshasa
	6 weeks
	$18,500.00

	02
	Schematic Design — Massing studies, renderings, climate-responsive design for DR Congo
	8 weeks
	$32,000.00

	03
	Design Development & Building Permit Submission to Commune de Lemba, Kinshasa
	12 weeks
	$45,000.00

	04
	Construction Documentation — Full drawing set, specifications, BOQ
	10 weeks
	$38,500.00

	05
	Construction Administration & On-Site Supervision in Kinshasa, DR Congo
	84 weeks
	$96,000.00

	06
	Regulatory Compliance & OARDC Registration Fees (DR Congo)
	One-time
	$4,200.00

	07
	Travel, Accommodation & Logistics within Kinshasa & DR Congo
	Full project
	$12,800.00

	08
	Contingency & Unforeseen Site Conditions (5%)
	Full project
	$12,350.00

	TOTAL QUOTATION ESTIMATE (Architect Services, Kinshasa, DR Congo)
	$259,350.00


Note: All costs in this Quotation Estimate are quoted in United States Dollars (USD). Payment shall be made in USD or its equivalent in Congolese Francs (CDF) at the exchange rate published by the Banque Centrale du Congo on the date of each invoice. This Quotation Estimate does not include third-party engineering fees (structural, geotechnical, environmental) which will be quoted separately by the Architect upon client request.
4. Payment Schedule
	Milestone
	Percentage
	Amount (USD)

	Contract Signing & Mobilization
	10%
	$25,935.00

	Completion of Schematic Design
	15%
	$38,902.50

	Building Permit Granted by Kinshasa Authorities
	20%
	$51,870.00

	Issuance of Construction Documents
	20%
	$51,870.00

	Monthly Progress Payments (Construction Phase)
	25%
	$64,837.50

	Project Handover & Final Certification
	10%
	$25,935.00


5. Terms & Conditions
· This Quotation Estimate is valid for a period of ninety (90) days from the date of issue. Beyond this period, the Architect reserves the right to revise all fees due to market fluctuations in Kinshasa, DR Congo.
· The Architect shall not be liable for delays caused by DR Congo government regulatory processes, force majeure events, or client-directed changes to the project scope in Kinshasa.
· All intellectual property rights in the architectural drawings and designs produced by the Architect remain with Studio Kongo Architectes until full payment of this Quotation Estimate is received.
· The Architect is registered with the OARDC and holds a valid professional license to practice architecture in the Democratic Republic of Congo. All services will be performed in accordance with the professional code of ethics of the DR Congo architectural profession.
· Any dispute arising from this Quotation Estimate or the subsequent contract shall be resolved through arbitration in Kinshasa, DR Congo, in accordance with the rules of the CCI Kinshasa.
· The client acknowledges that the Architect has the right to display the completed project in professional portfolios and publications, subject to the client’s written consent regarding confidentiality.
6. Acceptance & Authorization
By signing below, the client confirms acceptance of this Quotation Estimate for Architect services in Kinshasa, DR Congo, and authorizes Studio Kongo Architectes to proceed with the project as described herein.
For Studio Kongo Architectes (Architect)
Ing. Mireille Kabasele
Lead Architect, OARDC Reg. No. 2019-0447
Date: _______________
For Société ImmoKin SA (Client)
Authorized Representative
Name: _______________
Date: _______________
Studio Kongo Architectes — Avenue de la Paix, Gombe, Kinshasa, Democratic Republic of Congo
Tel: +243 990 000 000 | Email: info@studiokongo.cd | RCCM: 12345678/2019
This Quotation Estimate is a commercial document and does not constitute a binding contract until countersigned by both parties.
