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1. Project Overview & Scope of Architectural Services
This Quotation Estimate is issued by Nile Horizon Architectural Design Studio, a licensed Architect firm registered with the Chamber of Engineers in Egypt Cairo, in response to the client's request for comprehensive architectural design and consulting services. The project involves the design of a mixed-use residential and commercial complex comprising six (6) residential towers and a ground-level retail podium, situated on a 12,000 square meter plot in the New Cairo district, Egypt Cairo. Our Architect team will deliver all phases of design documentation in full compliance with the Egyptian Building Code, the Cairo Governorate Zoning Regulations, and the standards set forth by the National Organization for Control of Technical Specifications (NACS) in Egypt Cairo.
2. Itemized Quotation Estimate Breakdown
	No.
	Architect Service Description
	Phase / Deliverable
	Duration
	Unit
	Amount (EGP)

	1
	Site survey, topographic analysis, and feasibility study for the Egypt Cairo plot, including solar orientation and wind pattern assessment specific to the Cairo climate
	Pre-Design
	3 weeks
	Lump Sum
	85,000

	2
	Conceptual design development by the lead Architect, including massing studies, 3D renderings, and two (2) alternative design schemes for client review
	Concept Design
	6 weeks
	Lump Sum
	320,000

	3
	Schematic design documentation: floor plans, elevations, sections, and structural coordination drawings for all six towers and the retail podium
	Schematic Design
	8 weeks
	Lump Sum
	450,000

	4
	Detailed architectural design and construction documentation package, including specifications, material schedules, and MEP coordination, prepared to Egypt Cairo municipal submission standards
	Design Development
	12 weeks
	Lump Sum
	680,000

	5
	Construction drawings and tender documentation: 1:50 and 1:100 scale drawings, door and window schedules, finish schedules, and quantity take-off for contractor bidding
	Construction Docs
	10 weeks
	Lump Sum
	520,000

	6
	Permit application support: preparation and submission of all architectural drawings to the Cairo Governorate Building Permits Office, including revisions required by the Egypt Cairo review committee
	Permitting
	6 weeks
	Lump Sum
	120,000

	7
	Construction-phase Architect supervision: monthly site inspections, design queries resolution, as-built documentation, and punch-list management throughout the 24-month construction period
	Construction Admin
	24 months
	Monthly
	48,000 / mo

	8
	Interior design concept for the retail podium and lobby areas, including furniture layout, lighting design, and material palette selection aligned with Egypt Cairo aesthetic standards
	Interior Design
	8 weeks
	Lump Sum
	275,000

	9
	Landscape and external works design: parking layout, pedestrian pathways, green areas, and irrigation plan compliant with New Cairo urban planning guidelines
	Landscape Design
	5 weeks
	Lump Sum
	145,000

	10
	Project management coordination: weekly progress meetings, design change order processing, and final handover documentation package
	PM Coordination
	Full project
	Lump Sum
	195,000

	TOTAL QUOTATION ESTIMATE (EGP)
	3,895,000


3. Payment Schedule
This Quotation Estimate for Architect services in Egypt Cairo shall be paid according to the following milestone-based schedule:
· 15% upon signing of the Architectural Services Agreement (EGP 584,250)
· 20% upon approval of the Concept Design phase (EGP 779,000)
· 25% upon submission of Schematic and Design Development documentation (EGP 973,750)
· 20% upon issuance of Construction Drawings and tender package (EGP 779,000)
· 10% upon successful building permit approval by the Egypt Cairo Governorate (EGP 389,500)
· 10% distributed monthly during the Construction Administration phase (EGP 38,950 per month)
4. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any Architect services not commenced within this period will require a revised quotation.
· All prices are quoted in Egyptian Pounds (EGP) and are exclusive of Value Added Tax (VAT) at the prevailing rate of 14% as per the Egyptian Tax Authority regulations applicable in Egypt Cairo.
· The Architect firm reserves the right to adjust the Quotation Estimate in the event of scope changes exceeding 10% of the originally agreed deliverables.
· All intellectual property rights over the architectural designs, drawings, and documentation produced by our Architect team shall remain with Nile Horizon Architectural Design Studio until full payment is received.
· The client agrees to provide timely access to the project site in Egypt Cairo and to supply all necessary existing survey data, utility maps, and geotechnical reports within five (5) business days of the project kickoff.
· Disputes arising from this Quotation Estimate or the subsequent Architectural Services Agreement shall be resolved through arbitration in accordance with the rules of the Egyptian Arbitration Center, with the seat of arbitration in Egypt Cairo.
· Force majeure events, including but not limited to government-mandated shutdowns, natural disasters, or changes in Egypt Cairo building regulations, shall extend the project timeline proportionally without penalty to either party.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate for Architect services in Egypt Cairo and agrees to the terms, conditions, and pricing outlined herein. This signature constitutes a binding acceptance of the Quotation Estimate and authorizes Nile Horizon Architectural Design Studio to commence the Pre-Design phase.
For Nile Horizon Architectural Design Studio
Lead Architect / Authorized Signatory
Name: Eng. Mona Fathy Abdel-Rahman
License: CAIRO-ARCH-2019-0047
Date: _______________
For El-Sayed Real Estate Development Co.
Authorized Representative
Name: Mr. Ahmed Hassan El-Sayed
Title: Managing Director
Date: _______________
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