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Project Overview
This Quotation Estimate is issued by Addis Ababa Architectural Design Studio, a licensed Architect firm operating in the heart of Addis Ababa, Ethiopia, to provide a comprehensive cost breakdown for the design, planning, and architectural consultancy services required for the proposed 12-Storey Mixed-Use Commercial and Residential Building located on the Bole Sub-City, Addis Ababa. The Architect team will oversee all phases from conceptual design through to construction documentation, ensuring full compliance with the Ethiopian Building Code, the Addis Ababa City Administration Building Permit Regulations, and the Federal Ministry of Urban and Infrastructure Development standards.
Scope of Architectural Services
The Architect firm shall deliver the following professional services as part of this Quotation Estimate engagement in Addis Ababa, Ethiopia:
No.
Service Description
Deliverables
Duration
Cost (ETB)
1
Site Survey & Feasibility Study in Addis Ababa
Site report, topographic survey, geotechnical assessment, zoning compliance review per Addis Ababa City Planning Bureau
3 Weeks
185,000
2
Conceptual Design & Architectural Schematics
3D massing studies, floor plans, elevations, site plans, material palette, sustainability strategy aligned with Ethiopian green building guidelines
6 Weeks
420,000
3
Detailed Architectural Design & Construction Drawings
Full set of construction drawings (structural, MEP coordination, architectural details), BIM model (Revit), quantity take-off for tender documentation
10 Weeks
780,000
4
Building Permit Application & Regulatory Approval (Addis Ababa)
Preparation and submission of all documents to Addis Ababa City Building Permit Office, coordination with Ethiopian Environmental Protection Authority, fire safety compliance
4 Weeks
150,000
5
Tender Support & Contractor Coordination
Bill of Quantities preparation, clarification responses, contract administration support for the construction phase in Addis Ababa
5 Weeks
220,000
6
Construction Phase Architectural Supervision
Weekly site inspections, design compliance verification, variation order assessment, progress reporting to the client throughout the construction period in Addis Ababa, Ethiopia
18 Months
1,250,000
7
Interior Design & Landscape Architecture
Interior fit-out drawings for retail and residential units, landscape plan for ground-level plaza and rooftop garden using indigenous Ethiopian plant species
8 Weeks
340,000
8
As-Built Documentation & Handover
Final as-built drawings, O&M manuals, warranty documentation, and project close-out report
4 Weeks
95,000
TOTAL QUOTATION ESTIMATE AMOUNT
ETB 3,440,000
VAT (15% - Ethiopian Tax Authority)
ETB 516,000
GRAND TOTAL (Incl. VAT)
ETB 3,956,000
Payment Schedule
	Milestone
	Percentage
	Amount (ETB)

	Upon signing of this Quotation Estimate and service agreement
	20%
	791,200

	Upon approval of Conceptual Design
	15%
	593,400

	Upon submission of Construction Drawings
	25%
	989,000

	Upon receipt of Building Permit from Addis Ababa
	15%
	593,400

	Monthly during Construction Supervision (18 installments)
	20%
	791,200

	Upon Project Handover & As-Built Delivery
	5%
	197,800


Terms & Conditions
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. After this period, the Architect firm reserves the right to revise pricing due to market fluctuations in Addis Ababa, Ethiopia.
1. All costs are quoted in Ethiopian Birr (ETB) and are subject to the prevailing VAT rate as determined by the Ethiopian Revenue and Customs Authority. Any change in tax legislation during the project duration shall be reflected in a supplementary Quotation Estimate.
1. The Architect firm shall maintain professional indemnity insurance with a minimum coverage of ETB 10,000,000, as required by the Ethiopian Architects and Engineers Registration Board.
1. All intellectual property rights in the architectural drawings, BIM models, and design documents produced under this Quotation Estimate shall vest in the client upon full payment of the Grand Total amount.
1. The Architect shall comply with all applicable Ethiopian laws, including the Ethiopian Civil Code, the Urban Planning and Construction Proclamation (No. 920/2015), and Addis Ababa City Administration bylaws.
1. Any changes to the scope of work beyond the parameters defined in this Quotation Estimate shall be subject to a written variation order signed by both parties, with an adjusted cost estimate provided by the Architect within five (5) working days.
1. Disputes arising from this Quotation Estimate shall be resolved through mediation in Addis Ababa, Ethiopia, in accordance with the Ethiopian Arbitration and Conciliation Proclamation (No. 1221/2020).
1. The Architect firm shall not be liable for delays caused by government permit processing times at the Addis Ababa City Building Permit Office or force majeure events.
Important Note: This Quotation Estimate assumes standard working conditions in Addis Ababa, Ethiopia. Should the project site require special access arrangements, additional structural engineering input beyond the Architect's coordination scope, or expedited timelines, a revised Quotation Estimate shall be issued prior to commencement of the additional work.
For and on behalf of the Architect Firm:
Ar. Selamawit Bekele
Principal Architect, Addis Ababa Architectural Design Studio
Date: _______________
Accepted by the Client:
Mr. Dawit Tadesse
Managing Director, Tadesse Holdings PLC
Date: _______________
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