# Quotation Estimate - Architectural Services - Addis Ababa, Ethiopia

# QUOTATION ESTIMATE

Professional Architectural Design & Consulting Services

Quotation Reference No: QTE-ADD-2025-0472 | Date: 15 June 2025

### Prepared By (Architect)

Addis Ababa Architectural Design Studio

Led by: Ar. Selamawit Bekele, RIBA Chartered Architect

Bole Road, Near Friendship Hotel

Addis Ababa, Ethiopia

Tel: +251-11-662-3450

Email: info@addisarchstudio.et

License No: EAA-2019-00847

### Prepared For (Client)

Mr. Dawit Tadesse

Tadesse Holdings PLC

Kazanchis Avenue, Building 12, Floor 4

Addis Ababa, Ethiopia

Tel: +251-911-456-789

Email: dawit.tadesse@tadesseholdings.et

Project Overview

This Quotation Estimate is issued by Addis Ababa Architectural Design Studio, a licensed Architect firm operating in the heart of Addis Ababa, Ethiopia, to provide a comprehensive cost breakdown for the design, planning, and architectural consultancy services required for the proposed 12-Storey Mixed-Use Commercial and Residential Building located on the Bole Sub-City, Addis Ababa. The Architect team will oversee all phases from conceptual design through to construction documentation, ensuring full compliance with the Ethiopian Building Code, the Addis Ababa City Administration Building Permit Regulations, and the Federal Ministry of Urban and Infrastructure Development standards.

Scope of Architectural Services

The Architect firm shall deliver the following professional services as part of this Quotation Estimate engagement in Addis Ababa, Ethiopia:

No.

Service Description

Deliverables

Duration

Cost (ETB)

1

Site Survey & Feasibility Study in Addis Ababa

Site report, topographic survey, geotechnical assessment, zoning compliance review per Addis Ababa City Planning Bureau

3 Weeks

185,000

2

Conceptual Design & Architectural Schematics

3D massing studies, floor plans, elevations, site plans, material palette, sustainability strategy aligned with Ethiopian green building guidelines

6 Weeks

420,000

3

Detailed Architectural Design & Construction Drawings

Full set of construction drawings (structural, MEP coordination, architectural details), BIM model (Revit), quantity take-off for tender documentation

10 Weeks

780,000

4

Building Permit Application & Regulatory Approval (Addis Ababa)

Preparation and submission of all documents to Addis Ababa City Building Permit Office, coordination with Ethiopian Environmental Protection Authority, fire safety compliance

4 Weeks

150,000

5

Tender Support & Contractor Coordination

Bill of Quantities preparation, clarification responses, contract administration support for the construction phase in Addis Ababa

5 Weeks

220,000

6

Construction Phase Architectural Supervision

Weekly site inspections, design compliance verification, variation order assessment, progress reporting to the client throughout the construction period in Addis Ababa, Ethiopia

18 Months

1,250,000

7

Interior Design & Landscape Architecture

Interior fit-out drawings for retail and residential units, landscape plan for ground-level plaza and rooftop garden using indigenous Ethiopian plant species

8 Weeks

340,000

8

As-Built Documentation & Handover

Final as-built drawings, O&M manuals, warranty documentation, and project close-out report

4 Weeks

95,000

TOTAL QUOTATION ESTIMATE AMOUNT

ETB 3,440,000

VAT (15% - Ethiopian Tax Authority)

ETB 516,000

GRAND TOTAL (Incl. VAT)

ETB 3,956,000

Payment Schedule

| Milestone | Percentage | Amount (ETB) |
| --- | --- | --- |
| Upon signing of this Quotation Estimate and service agreement | 20% | 791,200 |
| Upon approval of Conceptual Design | 15% | 593,400 |
| Upon submission of Construction Drawings | 25% | 989,000 |
| Upon receipt of Building Permit from Addis Ababa | 15% | 593,400 |
| Monthly during Construction Supervision (18 installments) | 20% | 791,200 |
| Upon Project Handover & As-Built Delivery | 5% | 197,800 |

Terms & Conditions

- This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. After this period, the Architect firm reserves the right to revise pricing due to market fluctuations in Addis Ababa, Ethiopia.

- All costs are quoted in Ethiopian Birr (ETB) and are subject to the prevailing VAT rate as determined by the Ethiopian Revenue and Customs Authority. Any change in tax legislation during the project duration shall be reflected in a supplementary Quotation Estimate.

- The Architect firm shall maintain professional indemnity insurance with a minimum coverage of ETB 10,000,000, as required by the Ethiopian Architects and Engineers Registration Board.

- All intellectual property rights in the architectural drawings, BIM models, and design documents produced under this Quotation Estimate shall vest in the client upon full payment of the Grand Total amount.

- The Architect shall comply with all applicable Ethiopian laws, including the Ethiopian Civil Code, the Urban Planning and Construction Proclamation (No. 920/2015), and Addis Ababa City Administration bylaws.

- Any changes to the scope of work beyond the parameters defined in this Quotation Estimate shall be subject to a written variation order signed by both parties, with an adjusted cost estimate provided by the Architect within five (5) working days.

- Disputes arising from this Quotation Estimate shall be resolved through mediation in Addis Ababa, Ethiopia, in accordance with the Ethiopian Arbitration and Conciliation Proclamation (No. 1221/2020).

- The Architect firm shall not be liable for delays caused by government permit processing times at the Addis Ababa City Building Permit Office or force majeure events.

Important Note: This Quotation Estimate assumes standard working conditions in Addis Ababa, Ethiopia. Should the project site require special access arrangements, additional structural engineering input beyond the Architect's coordination scope, or expedited timelines, a revised Quotation Estimate shall be issued prior to commencement of the additional work.

For and on behalf of the Architect Firm:

Ar. Selamawit Bekele
Principal Architect, Addis Ababa Architectural Design Studio
Date: _______________

Accepted by the Client:

Mr. Dawit Tadesse
Managing Director, Tadesse Holdings PLC
Date: _______________

Addis Ababa Architectural Design Studio | Bole Road, Addis Ababa, Ethiopia | License: EAA-2019-00847

This Quotation Estimate document is issued in duplicate. One copy for the Architect firm and one copy for the client. Both copies carry equal legal validity under Ethiopian law.

© 2025 Addis Ababa Architectural Design Studio. All Rights Reserved.